## Status AP PFM 2018_EN
PRIORITY |  |  |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION | OTHER INSTITUTIONS INVOLVED | INDICATOR | INDICATOR TARGET 2018 | STATUS
MEASURE
|  |  | ACTIVITY/SUB-ACTIVITY | START | END
P1 Improved Fiscal Framework
P1M1 Formulation, adoption and implementation of fiscal rules
|  | P1M1A1 | Designing of fiscal rule and adoption of the fiscal rule legislation | Q1 2018 | Q4 2019 |  |  | a) Draft Fiscal rules design b) Adoption of the fiscal rule legislation | a) Fiscal rules designed b) Fiscal rules legislation adopted
|  |  | Analysis of the already given recommendation and data collected for the fiscal rules | 2017 | 2018 | MoF | /
|  |  | Consultation with the services of the European Commission and international financial institutions on developing the concept for application and follow-up of fiscal rules IMF Technical mission of short- term expert for fiscal rules In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS. In this regards fiscal rules will be part of this project | Q1 2018 | Q4 2018 | MoF | EU, IMF, WB foreign and local experts |  |  | IMF fiscal expert Steve Symansky carried out short-term technical mission in the period from 12th to 27th February 2018. Draft Report was prepared, containing recommendations on designing the framework for implementation of the Fiscal Rules and the Fiscal Council, in line with the conditions in the Republic of Macedonia.
|  |  | Legal changes for institutionalizing the Fiscal Council In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS. In this regards fiscal rules will be part of this project (year, experts and budget as written above) | 2018 | 2019 | MoF | Assembly |  |  | New/revised Budget Law is in the process of preparation, envisiging institutionalization of the Fiscal Council.
| P1M2 | Strengthening of forecasting
|  | P1M2A1 | Reorganization of organisation structure and responsibilities in charge of revenues projections | Q1 2018 | Q4 2018 |  |  | Adoption of new systematization with clear role of responsibilities for tax and non-tax revenue projections | Systematization adopted
|  |  | Analysis of the current process of revenue projections based on the best practices in the EU member countries and recommendations for their improvements - Twinning project “Strengthening the medium term budgeting for effective public financial management" 2015-2017 | Q1 2018 | Q4 2018 | MoF departments | / |  |  | Draft amendment to the Rulebook on Organization and Operations of the Ministry of Finance is prepared, aimed at reorganizing the organizational set-up and the responsibilities related to tax projections of tax revenues, in order for it to be taken into account in the next amendment of the Rulebook.
|  | P1M2A2 | Strengthening the capacities for tax revenue planning | Q4 2018 | Q4 2019 |  |  | a) Employment of sufficient staff for tax revenue projections | /
|  |  | Start of procedure of recruiting new staff for tax revenue projections | Q4 2018 | Q2 2019 | MoF departments
|  | P1M2A4 | Further development of the macroeconomic model | Q3 2018 | Q4 2018 | MoF |  | a) Revision of methodology of the model's supply side b) Inclusion of new quarterly national accounts time series in the model | Methodology revised
P2 Revenue Mobilization
P2M2 Improved tax and customs services and procedures
|  | P2M2A1 | Implementation of the project activities foreseen in the PROs Modernisation Programme (including reengineering of business processes, new Tax Integrated IT system) | Q1 2016 | Q1 2021 | PRO
|  |  | Introducing E-submission of the “Calculation for all personal income payments (except the payments of salary)“; | Q4 2016 | Q4 2019 | PRO | MoF | E-submission of the “Calculation for all personal income payments (except the payments of salary)“ | “To-Be” business process and new software, developed, tested and introduced | MoF: Introduced in the Law on Modifications and Amendments to the Law on Personal Income Tax, published in the "Official gazette of the Republic of Macedonia", no. 190, dated 25 December 2017, to be applied starting 1 January 2018. The goal of adopting the Law is to change the so-far concept of filling in and submitting the annual tax return (ATR). In fact, instead of the citizens, the PROwill fill in their ATR and it will submit the ATR to them for confirmation. PRO: IPA 2012 PPF Project “Simplification of procedures for reporting and payment of Personal Income Tax for taxpayer – individuals” started on 1 December 2016 and ended on 3 April 2018: - Law on Modifications and amendments to the Law on PIT and Rulebook on the Manner of Calculation and Payments of Advanced Personal Income Tax, the Form and the Contents and the Manner of Submission and Approval of the Electronic Calculation for Income and Tax entered into force as of 1 January 2018, thus setting the framework for submission of the electronic calculations for tax for each payment of income to a natural person (except salary) by the payer and for each income generated by a natural person from another natural person in the country and abroad; - new electronic PRO system e-Personal Tax https://e-pdd.ujp.gov.mk is in function as of 1 January 2018, providing the taxpayers with the service for preparation and submission of the electronic calculations for income and tax with direct input of data or reading data prepared with appropriate structure, providing accuracy of the data in the electronic calculation by the system, and based on the built in controls and submits automatic electronic payment order to the carriers of the payment operations; - series of trainings for the taxpayers are held to introduce the manner and the functioning of the electronic calculation for income and tax.; To-Be business processes and software ate developed and tested through the Project and within the new PRO electronic system e–Personal Tax https://e-pdd.ujp.gov.mk, which will provide for issuance of pre-populated Annual Tax Return by PRO in 2019, in line with the amendments of the Law on Personal Income Tax in force as of 1 January 2018.
|  |  | Introducing Pre-populated Annual Tax Return by PRO |  |  |  |  | Issuing pre-populated Annual Tax Return by PRO | “To-Be” business process and new software, developed and tested
|  |  | Supply of IT equipment for upgrading the electronic tax system "Upgrade of the e-Tax system" and the Project "Simplification of the procedures for reporting and payment PIT for Citizens". | Q4 2016 | Q4 2018 | PRO |  |  |  | The equipment is supplied. The installation of the equipment, according to the signed contract between PRO and the selected contractor, is ongoing.
|  |  | Improving the Contact Centre and Tax Counters Services (introducing new CC web page, Appointment System, Informa - Knowledge Base, Queuing System, integrated CC IT System, Mobile Tax Counters etc.) | Q4 2014 | Q4 2019 | PRO | / | Improved Contact Centre and Tax Counters Services | IT equipment for strengthening the capacity of the PRО – Contact Centre/Call Centre delivered | Within the IPA 2 / EUIF 2014 Project "Supply of IT Equipment for Strengthening the Capacity of the PRO Contact Center / Call Center", IT equipment for strengthening the capacity of the PRO - Contact Center / Call Center was delivered on 16 March 2018. Activities for completion of the Project are underway.
|  |  | Strengthening of PRO staff and new recruitments *** total of 35 new employments planned in the year (41,103.36 MKD or 672 EUR average monthly gross salary for each new employment); *** total of 70 new reassignments planned per year (7,204.45 MKD or 118 EUR costs for average monthly gross salary for each reassignment (promotion) for current staff) | Q1 2018 | Q4 2018 | PRO | MoF |  |  | An Annual Plan for Employment for 2018 has been prepared, for which consent from the Ministry of Finance has been obtained, and technical adjustments are ongoing with the Secretariat for Implementation of the Framework Agreement and the Ministry of Information Society and Administration for obtaining consent, followed by its adoption by the Director of PRO (foreseen: 38 retirements, 35 new employments and 70 promotions). The procedure for adoption of the Annual Plan for Employment for 2019, for which consent from the Ministry of Finance has been obtained, while the approval from the Secretariat for Implementation of the Framework Agreement, and then the Ministry of Information Society and Administration, followed by its adoption by the Director of PRO is ongoing (provided: 36 retirements, 35 new employments and 70 promotions). As of 31 April 2018, following has been realized in the Public Revenue Office: - (5) Internal competitions for promotion of (29) tax officers have been performed, whereby (23) are promoted and (1) internal competition for promotion of (5) tax officers is ongoing; - (1) Internal competition for promotion of administrative / civil servants carried out and (1) civil servant promoted; - (62) permanent reassignments of tax officers performed for ensuring adequate human resource planning and timely performance of the functions in scope, the quality and the deadlines determined by the work programs. - 10 new temporary employments performed; - (1) new employment performed in the mobility procedure by taking over from other institutions.
|  |  | Development and re-engineering of business processes for the new tax integrated IT system (prepare and deliver a Business Process Modeling (BPM2) showing global scheme of business processes which should be re-engineered and integrated in the new IT system (“TO-BE” system): supply - BMP software and licenses; Technical Specification for New tax integrated IT system hardware and software and for quality assurance - technical support for implementation) | Q4 2017 | Q4 2019 | PRO | MoF/МИОА | Re-engineered business processes for the new tax integrated IT system; New tax integrated IT system HARDWARE; New tax integrated IT system SOFTWARE; Quality Assurance technical support for implementation of the new integrated IT system, provided for PRO. | Prepare and deliver a Business Process Modeling (BPM2) showing global scheme of business processes which should be re-engineered and integrated in the new IT system (“TO-BE” system) Technical Specification prepared Technical Specification prepared Technical Specification prepared | On 1 November 2017, started the implementation of the IPA 2 / EUIF 2014 Project "Development and Reengineering of Work Processes for the New Integrated IT System" started on 1 November 2017, through which these PFM activities should be realized within 15 months.
|  |  | Establishment of new Data IT System Centre | Q1 2018 | Q4 2019 | PRO | / |  |  | PRO Annual Plan for Public Procurement in 2018, adopted on 31 January 2018 (please see http://www.ujp.gov.mk/mk/osnovni_dokumenti/category/1557), procurements are foreseen for realization of this PFM activity - Establishment of IT system hall, i.e.: 1) Design and supervision of IT system hall; 2) Supervision during the performance of works for renovation of the IT system hall; 3) Renovation of IT system hall.
|  |  | Upgrade of current PRO IT sub-systems and equipment, maintaining, licenses etc. (upgrade and maintenance of e-Personal Tax system including registration, submission of calculation, control and data transfer for salary payments; upgrade and maintenance of e-Tax system; upgrade of tax accounting system) | Q1 2018 | Q4 2019 | PRO |  |  |  | 1. Upgrade and maintenance of e-Personal tax (planned amount of 12,000,000 MKD, complete tender documentation has been prepared and technical dialogue is ongoing in accordance with the Law on Public Procurement) The upgrade of the e-Personal Tax system with the User Modules for Integrated Collection of Contributions and personal tax on salary and for taxation of entrepreneurs on real-income, should enable administering of the personal tax through one system for all categories of taxpayers and for all types of income subject to taxation with PIT, rather than through separate systems. At the same time, the project should enable sustainability of the systems and their day to day maintenance, as well as the possibility for their adjustment to the changes in the legislation. 2. Software with licenses for the development and re-engineering of business processes for the new integrated tax IT system of the Public Revenue Office (planned amount of 1,600,000 MKD, approval of the prepared tender documentation with Decision for Public Procurement is ongoing) 3. Upgrading of the application for tax accounting (planned amount of 5,000,000 MKD, technical specification has been prepared, preparation of tender documentation with Decision for Public Procurement is ongoing).
|  |  | Development and introducing Risk Evaluation System – RES in PRO | Q1 2017 | Q4 2019 | PRO | / | Risk Evaluation System – RES for tax audit | Risk Evaluation System – RES Software developed and implemented | Implementation of the Project "Risk Evaluation System" (donation of Austrian Development Agencies (ADA) & WedoIT-Solutions GmbH) started on 14 June 2017, which should provide for establishment of an objective and accurate selection of taxpayers for control, by promoting the process of risk analysis in the external control and taxpayers' compliance risk management. The new software is in the testing phase with real data on the test base.
|  | P2M2A2 | Strengthening operational capacities of CARM to increase the quality of controls and responses and introducing further simplification of procedures | Q1 2016 | Q4 2021 | CARM |  | a) Number of decisions to use simplified procedures increased i) Master Plan to overcome gaps and needs prepared ii) Action Plan and technical specification prepared iii) Number of trained customs officers and teconomic operators according the Plan | /
|  |  | Drafting the Twinning Fiche including this component as part of one Twinning Fiche under IPA 2 - 2018 | Q1 2018 | Q4 2018 | CARM | EUD |  |  | There are ongoing consultations for determination of the areas that the Twinning Fiche will cover, as well as coordination with other activities of domestic institutions and foreign partners.
|  | P2M2A3 | Introducing enhanced models and methods to strengthen the control system to prevent, detect and fight against customs frauds and illegal trafficking of goods while facilitating the trade | Q1 2018 | Q4 2021 | CARM |  | a) No of financial investigations conducted i) Plan to overcome gaps and needs prepared ii) Upgrade of equipment and tools used by the customs officers to implement and enforce enhanced models and methods of controls | /
|  |  | Analyses of gaps, needs to increase the quality of controls and responses throughout the country and Drafting this component as part of one Twinning Fiche under IPA 2 - 2018 | Q1 2018 | Q4 2018 | CARM | EUD |  |  | There are ongoing consultations for determination of the areas that the Twinning Fiche will cover, as well as coordination with other activities of domestic institutions and foreign partners.
P3 Planning and Budgeting
P3M1 Upgraded programme based budget approach and improved project information
|  | P3M1A1 | Implementation of the proposed program based budgeting approach | Q1 2018 | Q4 2021 |  |  | a) Improvement of methodology and guidelines for new programme budgeting b) Trainings for programme budgeting conducted c) % of budget users applying new classification | a) / b) Trainings conducted c) 0
|  |  | Strengthening the capacities of the Ministry of Finance and the budget users for appropriate implementation of budget programmes In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS. In this regards budget program classification will be part of this project | 2018 |  | MoF and budget users | Foreign and domestic experts |  |  | Technical assistance mission was carried out in December 2017 with the assistance of IMF, whereby the existing documents, produced within the Short-Term Budgeting Twinning project, were analyzed and a Mission Report was prepared with guidelines for the procedures and the operation of MoF in the coming period. Short-term mission with a IMF expert took place in February aimed at revising the first version of the Budget Law - Mission report is prepared. In addition, MoF is in the stage of negotiations with potential donor for the preparation of budget regulations in line with the improvement of the PFM system, detailed planning of all working processes in PFM and preparation of technical specification on the integrated Financial Management Information System.
|  |  | Process analysis, monitoring and control of programme budgeting In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS. In this regards budget program classification will be part of this project Concept for monitoring of programme budgeting will be developed. Costs and experts are the same as mentioned above | 2018 |  | MoF and budget users
|  |  | Identify recommendations for improvement programme base budget IMF expert- TA mission- held in December 2017 for Organic budget law In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS. In this regards budget program classification will be part of this project Costs and experts are the same as mentioned above. | 2017 | 2018 | MoF | IMF expert - TA mission held in December 2017 for Organic budget law foreign and domestic experts
|  | P3M1A2 | Conduct Public Investment Management Assessment (in collaboration with IMF) | Q1 2018 | Q4 2018 |  |  | Report from the conducted assessment | Report prepared 2019
|  |  | New deadline | Q4 2018 | Q3 2019
|  |  | Engagement of the team for the assessment | end 2018/19 | 2019 | Ministry of finance and other relevant institutions that have capital projects | IMF
|  |  | Meetings and cooperation with all relevant institutions | end 2018/19 | 2019 | Ministry of finance and other relevant institutions that have capital projects | IMF
|  |  | Providing data and documents | end 2018/20 | 2019 | Ministry of finance and other relevant institutions that have capital projects | IMF
P3M3 Revised Organic Budget Law in line with the improvements of the PFM system
|  | P3M3A1 | Preparation and adoption of new/revised organic budget law | Q1 Q4 2017 | Q4 2018 |  |  | New organic budget law prepared | New organic budget law adopted
|  |  | Analyses of the current data, documents and proposals provided by the IPA project IMF expert- TA mission- held in December 2017 In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS | 2017 | 2018 | MoF | IMF expert - TA mission: - TA mission held in December 2017 - short TA mission- in February 2018 foreign and domestic experts IMF expert- TA mission foreign and domestic experts |  |  | Technical assistance mission was carried out in December 2017 with the assistance of IMF, whereby the existing documents, produced within the Short-Term Budgeting Twinning project, were analyzed and a Mission Report was prepared with guidelines for the procedures and the operation of MoF in the coming period. Meetings with the relevant departments within MoF were held within the Mission, which gave their contribution as regards the legal amendments and modifications. Short-term mission with a IMF expert took place in February aimed at revising the first version of the Budget Law - Mission report is prepared. An expert was engaged in April in cooperation with the World Bank, who worked on the draft Public Entities Registry, which is to be included in the new Law, as well as the draft Organizational Classification, also as part of the new Budget Law. In addition, MoF is in the stage of negotiations with potential donor for the preparation of budget regulations in line with the improvement of the PFM system, detailed planning of all working processes in PFM and preparation of technical specification on the integrated Financial Management Information System
|  |  | Preparation of a new/revised organic budget law IMF expert- TA mission- held in December 2017 In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS | 2017 | 2018 | MoF | IMF expert- TA mission foreign and domestic experts
|  |  | Consultation with all relevant departments in the MoF IMF expert- TA mission- held in December 2017 In phase of negotiating with potencial donors for working of the budget legislation in line with the improvements of the PFM System, mapping of all working processes in PFM and technical specification of IFMIS | 2017 | 2018 | MoF | IMF expert- TA mission foreign and domestic experts
|  |  | Adoption of a new/revised organic budget law |  | 2018 | Assembly
P4 Budget Execution
| P4M1 | Implementation of new financial management information system (FMIS)
|  | P4M1A1 | Introduction of IBAN accounts | Q1 2018 | Q1 2019 | MoF | NBRM (central bank), KIBS (banks), PRO, Customs, Social funds, Budget Beneficiaries | a) Establishment of working groups b) Preparation and adoption of new rulebook with forms and procedures c) % of transactions processed via new IBAN accounts | a) Working groups introduced b) New rulebook (for using IBAN accounts) adopted c) 30 % (of transactions processed via new IBAN accounts) | Activities under this measure have not been commenced yet. Preparation of Project proposal is ongoing, in cooperation with World Bank Trust Fund. This measure is expected to be part of the Project, which would be more comprehensive, including activities which are part of other priorities within the PFM Program.
|  |  | Set up joint teams to oversee the development and introduction of the changes affecting each institution | Q1 2018 | Q1 2018 | MoF | NBRM (central bank), KIBS (banks), PRO, Customs, Social funds, Budget Beneficiaries
|  |  | Define new rulebook with forms and procedures | Q2 2018 | Q3 2018 | MoF | NBRM (central bank), KIBS (banks), PRO, Customs, Social funds, Budget Beneficiaries
|  |  | Modify own software to process collection of revenues and payments | Q2/2018 | Q3/2018 | MoF | NBRM (central bank), KIBS (banks), PRO, Customs, Social funds, Budget Beneficiaries
|  |  | IIntroduce IBAN accounts gradually | Q3/2018 | Q1/2019 | MoF | NBRM (central bank), KIBS (banks), PRO, Customs, Social funds, Budget Beneficiaries
P4M2 Strengthening commitment controls
|  | P4M2A1 | Preparation of the report on the timeliness of entering the commitment data | Q1 2018 | Q4 2019 | MoF | budget users | (% ) Number budget beneficiaries which corrected their actions/ Number of BB that have failed to report | 50 ((%) Number budget beneficiaries which corrected their actions/ Number of BB that have failed to report)
|  |  | Creating register of Budget users who failed to report expenditure arrears in a timely manner | Q1 2018 | Q4 2019 | MoF | budget users |  |  | Law on Reporting and Recording of Liabilities was adopted and published in the "Official Gazette of Republic of Macedonia", no. 64/18. It came in force on 19 April 2018, while its application will commence on 19 may 2018. By starting applying the Law, the entities covered will have to report and record the liabilities in the Electronic System on Reporting and recording Liabilities.
|  |  | Preparing quarterly reports on budget users who failed to report expenditure arrears in a timely manner and publishing them on the Ministry's website | Q1 2018 | Q4 2019 | MoF | budget users |  |  | On the basis of the provisions in the Law, MoF will publish the summary reports on recorded data on quarterly basis. The first quarterly report will be produced after September 2018.
P4M3 Strenghtening debt management
|  | P4M3A1 | Revision of the debt legislation | Q4 2017 | Q4 2018 |  |  | Adopted amendments to the Public debt law | Adopted amendments to the Public debt law
|  |  | Preparation of the amendments to the Public Debt Law | Q1 2018 | Q1 2018 | MoF | / |  |  | Ongoing activity. Draft proposal are submitted by the WB experts and preparation of amendments and modifications to the Law is ongoing at the moment.
|  |  | Workshop for drafting amendments to the Public Debt Law organised by World bank Treasury under GDRM Program | Q1 2018 | Q2 2018 | MoF | WB, NBRM, SAO |  |  | Realized activity. Two-day workshop was organized in Mavrovo within GDRM (Government Debt and Risk Management) Project of the World Bank, where WB experts and the participants discussed all possible amendments to the Public Debt Law. MoF representatives (International Finance Relations and Public Debt Management Department, Budget Department, Tresory Department and Claim Collection Department), as well as representatives from NBRM, SAO and the Legislative Secretariat.
|  |  | Adoption of the amendments to the Public debt Law | Q3 2018 | Q4 2018 | Assembly | /
|  | P4M3A3 | Supplementing current risk indicators for refinancing and interest rate risk | Q3 2017 | Q2 2019 |  |  | New indicators for risk measurement introduced | /
|  |  | Capacity building/ trainings | Q3 2017 | Q2 2019 | MoF | World Bank |  |  | Ongoing activity. Mission took place within the GDRM Project, aimed at improving the Public Debt Management Strategy. In addition, several employees from the Department attended training organized by IMF and the World Bank, covering topics on public debt management.
|  |  | Strengthen the analytical foundation of the debt management strategy | Q4 2018 | Q2 2019 | MoF
|  | P4M3A4 | Strengthening human capacities | Q4 2017 | Q1 2020 |  |  | number of newly employed staff | 2 new recriutments
|  |  | Vacancy announcement | Q1 2018 | Q1 2020 | MoF
P4M4 Strengthening public procurement system
|  | P4M4A1 | Streamlining (revision) of the mandate and responsibilities of the institutions involved in the public procurement system | Q3 2017 | Q4 2017 |  |  | а) Modified competencies of relevant institutions in public procurement in accordance with the analysis according the SIGMA Report b) Number of newly recruited staff | a) Improved distribution and regulation of central public procurement functions b) 18 new recruitments
|  |  | Amendments were made to the Law on Public Procurement ("Official Gazette of the Republic of Macedonia" No. 165/2017) in November 2017, thus abolishing Public Procurement Council | Q3 2017 | Q4 2017 | MoF_PPB |  |  |  | This activity was completed in 2017.
|  |  | New Law on Public Procurement | Q2 2018 | Q4 2018 | MoF_PPB | SACPP |  |  | Draft version of the new Public Procurement Law envisages new expanded competences of the Public Procurement Bureau. This activity is to be realized with the adoption of the new Law. Activity - new Public Procurement Law is within P4M4A2, sub-activity 2.
|  |  | Strengthening the capacities of PPB | Q2 2018 | Q4 2018 | MoF | PPB |  |  | Taking into account that new expanded competences of the Public Procurement Bureau are envisaged in the new Law, 18 new employments are needed. Envisaged activity has not started to be realized yet.
|  | P4M4A2 | Harmonisation of the Public Procurement legal framework with the acquis | Q4 2017 | Q4 2018 |  |  | a) Level of alignment with EU acquis b) Competition rate: - one bid tender (only from electronic procedures) | a) Legislation harmonised with EU acquis b) 25% (Competition rate: - one bid tender (only from electronic procedures))
|  |  | First Draf of the new Law on Public Procurement | Q3 2017 | Q1 2018 | PPB | MoF; SACPP |  |  | This activity is completed. First draft version of the new Public Procurement Law was published on the Single National Electronic Registry (ENER) in February 2018.
|  |  | Drafting new Law on Public Procurement harmonised with new EU directives | Q1 2018 | Q2 2018 | PPB | MoF; SACPP |  |  | Second draft version of the new Public Procurement Law was published on the Single National Electronic Registry (ENER) in May 2018. Consultations were made as regards the first draft version, and the remarks contributing to improvment of the text of the Law were incorporated. Deadline for submission of comments and remarks for the second draft Public Procurement Law was 18 May. In parallel, technical meeting scheduled with DG NEAR in Brussels within theSubcommittee on Internal Market and Competition. The meeting will take place on 31 May, when comments and remarks at technical level are expected to be obtained.
|  |  | Adoption of the new Law on Public Procurement | Q2 2018 | Q4 2018 | MoF_PPB | SACPP
|  | P4M4A3 | Institutional strengthening of the public procurement system, including the review set-up | Q2 2018 | Q4 2020 |  |  | a) Nature and extent of clear user friendly guidelines and instructions standard documents and other tools available to CA and Procurement officials SIGMA Report b) Number of trained procurement officers per year c) % of decisions of the State Appeal Commission challenged at the Administrative court and % of Appeal commission decisions cancelled | a) Sufficient recognition in SIGMA Report b) Minimum 300 procurement officers trained for first time c) 10,69% complaints challenged to the next judicial level 20,73% of Appeal commission decisions cancelled
|  |  | Drafting the Twinning Fiche including this component as part of one Twinning Fiche under IPA 2 - 2018 | Q2 2018 | Q1 2019 | PPB | MoF |  |  | Guidelines are expected as whether the project will be approved by the EC. No activities have been undertaken so far.
|  | P4M4A4 | Introduction of an E-Appeal system | Q2 2017 | Q2 2019 |  |  | a) % of appeals submitted electronically via the e-Appeal system (+ raising trend) b) Introduction of new modules on ESPP c) New Law on Public Procurement and bylaws | a) 0 b) No of new modules c) Adopted Law on Public Procurement and bylaws
|  |  | Preparing the draft and final specifications by PPB and hired local consultant - Phase 1 | Q2 2017 | Q4 2017 | PPB | WB |  |  | This activity was completed in 2017.
|  |  | Adopting the specifications - Phase 1 | Q4 2017 | Q4 2017 | PPB |  |  |  | This activity was completed in 2017.
|  |  | Implementing the necessary changes in Law on PP and bylaws - Phase 2 | Q2 2018 | Q4 2018 | PPB | MoF |  |  | The new draft Public Procurement Law envisages the possibility for an e-appeal. The activity related to the new Public Procurement Law falls within P4M4A2, sub-activity 2.
|  |  | Development of new modules - Phase 2 | Q1 2018 | Q2 2018 | PPB |  |  |  | Development of new modules on e-appeal is part of the Action Plan for Upgrading the ESPP, arising from the new Public Procurement Law. This activity will be realized with a delay, and there are no obstacles for its realization.
|  |  | Implementation of the new modules on the ESPP - Phase 2 | Q2 2018 | Q3 2018 | PPB |  |  |  | This activity depends on the realization of the previous activity.
|  | P4M4A5 | Development of Integrity-related reports with procurement performance indicators and governance (anti-corruption) red flags | Q3 2017 | Q3 2018 |  |  | Developed methodological tools for fostering its implementation with aim of more efficient prevention and suppression of irregularities | Development of “red flags indicators” on ESPP
|  |  | Preparing the draft and final specifications by PPB and hired international consultant - Phase 1 | Q3 2017 | Q1 2018 | PPB | WB |  |  | First draft version was prepared by the engaged expert. Although the initial draft was submitted, the expert is late as regards the envisaged realization. PPB informed WB thereof, and further steps will be agreed with WB.
|  |  | Adopting the specifications - Phase 1 | Q1 2018 | Q1 2018 | PPB |  |  |  | First draft version was prepared by the engaged expert. Although the initial draft was submitted, the expert is late as regards the envisaged realization. PPB informed WB thereof, and further steps will be agreed with WB.
|  |  | Development of new modules - Phase 2 | Q1 2018 | Q2 2018 | PPB |  |  |  | This stage depends on the realization of the previous stage.
|  |  | Implementation of the new modules on the ESPP - Phase 2 | Q2 2018 | Q3 2018 | PPB |  |  |  | This stage depends on the realization of the previous stage.
|  | П4M4A6 | Introducing the obligation to publish the annual public procurement plans | Q1 2018 | Q4 2021 |  |  | a) Percentage of published procurement plans of the CA on ESPP b) Adoption of new Law on Public Procurement which will introduce legal obligation for contracting authorities to publish annual procurement plans | a) 0% of published procurement plans by CA b) Adopted new Law on Public Procuremen
|  |  | Adoption of new Law on Public Procurement which will introduce the legal requirement to publish the annual procurement plans | Q2 2018 | Q4 2018 | MoF_PPB | SACPP |  |  | The obligation is envisaged in the new draft Public Procurement law. The activity related to the new Public procurement Law falls within P4M4A2, sub-activity 2.
|  | P4M4A7 | Publishing of the concluded public contracts and their amendments | Q4 2017 | Q4 2021 |  |  | Percentage of published concluded contracts and amendments | 100% published public contracts | Taking into account that PPB, in line with its competences, monitors the timly delivery of the concluded contracts on the ESPP, fully automated process on mandatory uploading of concluded contracts is established. When filling in the Contract Award Notice and the Records on Simplified Competitive Procedure, it is mandatory to upload the concluded contract as well. On the contrary, the system would not allow for publication of the Contract Award Notice or the Records on Simplified Competitive Procedure. Should, as regards particular contract notice, no Contract Award Notice or Records on Simplified Competitive Procedure be published, ESPP will block the EO profile for further publishing of contract notices.
|  |  | New module for publishing of the concluded public contracts | Q4 2017 | Q4 2017 | PPB | Government |  |  | This activity was completed in 2017. To the end of raising the level of transparency and accountability in public procurement, Electronic System for Public Procurement is upgraded, thus providing for publishing of awarded public contracts. In December 2017, Government of the Republic of Macedonia obliged all contracting authorities to publish the concluded contracts on the ESPP, thus ensuring full insight for the public in such contracts.
|  |  | Adoption of a new Law on Public Procurement which will introduce the legal requirement for publishing the awarded public contracts | Q2 2018 | Q4 2018 | MoF_PPB |  |  |  | The obligation for publishing the annual plan is envisaged in the new draft Public Procurement law. The activity related to the new Public procurement Law falls within P4M4A2, sub-activity 2.
|  | P4M4A8 | E-Marketplace for small value procurement and e – catalogues | Q1 2018 | Q4 2020 |  |  | No of recommendations for implementation of new procurement tools: e-marketplace for small value procurement and e-catalogues | Strategy accompanied with a list of recommendations and best practice scenarios
|  |  | Technical assistance for development of strategy and recommendations for implementation of new procurement tools: e-marketplace for small value procurement and e-catalogues | Q1 2018 | Q2 2018 | PPB |  |  |  | Expert consultant was selected and contract was concluded. First draft version was prepared by the engaged expert. Public Procurement Bureau is considering the submitted documents.
| P4M5 | Effective PPP and concessions system
|  | P4M5A1 | Establish/upgrade/unify and publish register of PPPs | Q2 2018 | Q2 2019 | Ministry of Economy (MoE) |  | Comprehensive, timely and reliable data on concluded agreements for the establishment of a public-private partnership | Transparency of contracts establishing a public private partnership
|  |  | Analysis of the possibility and the manner of upgrading the E-auctions system in the ME in the direction of establishing a single system for awarding contracts for establishing a public private partnership, ie a system through which the announcements for awarding this type of contracts will be published, the entire procedure will be implemented and it will finally contain the register of concluded contracts (a sublimated system for awarding contracts for the establishment of a public-private partnership from start to finish) | Q2 2018 | Q3 2018 | МoЕ | MoF, PPB |  |  | Since the upgrading / establishment of the system imposes the need to amend the Law on Concessions and Public-Private Partnerships, in the forthcoming period, along with the implementation of the activity for transposing the Concession Directive, an analysis of the law and the by-laws with draft models for intervention in the same.
|  |  | Consultation with IT experts and preparation of draft specification for upgrade / establishment of the single electronic system for public private partnership | Q3 2018 | Q3 2018 | МoЕ |  |  |  | There have been preliminary consultations with IT experts (the economic operator who maintains the existing ESEA in the MoE).
|  |  | Implement the necessary changes in the law and bylaws | Q4 2018 | Q4 2018 | МoЕ | PPB
|  | P4M5A3 | Harmonisation of legislation in line with relevant EU acquis | Q4 2017 | Q4 2018 | МoЕ and MoF |  | Level of compliance with EU legislation | Adopted amendment to the Law on Concessions and Public Private Partnership
|  |  | Establishment of an inter-ministerial working group to draft the Law Amending the Law on Concessions and Public Private Partnership | Q1 2018 | Q1 2018 | МoЕ and MoF |  |  |  | Procedure for the establishment of the Working Group is in the final stage. After staffing and equipping the WG, it will start operating from June.
|  |  | Preparation of analysis and concept proposal for amending the Law on Concessions and Public Private Partnership | Q2 2018 | Q2 2018 | МoЕ and MoF | PPB, MoF, MoTC, MoCulture, MoEPP, MoAFWE, Cabinet of the DPM for Economic Affairs, Secretariat for Legislation, SEA
|  |  | Drafting the Law Amending the Law on Concessions and Public Private Partnership | Q2 2018 | Q3 2018 | МoЕ and MoF | PPB, MoF, MoTC, MoCulture, MoEPP, MoAFWE, Cabinet of the DPM for Economic Affairs, Secretariat for Legislation, SEA
|  |  | Preparation and adoption of the Law on Amending the Law on Concessions and Public Private Partnership | Q4 2018 | Q4 2018 | МoЕ and MoF | PPB, MoF, MoTC, MoCulture, MoEPP, MoAFWE, Cabinet of the DPM for Economic Affairs, Secretariat for Legislation, SEA
P5 | Transparent Government Reporting
| P5M1 | Improved transparency through government reporting
|  | P5M1A1 | Development and implementation of transparency standards for PFM reporting | Q1 2018 | Q4 2021 |  |  | New fiscal information published | a) Quarterly budget execution reports per budget user b) Quarterly and semi-annual budget execution reports of the local self-government units c) Quarterly reports on budget execution of the general government (consolidated report of the Budget of the Republic of Macedonia and of the budgets of the local self-government units) | Realized and will be realized continuously.
|  |  | Additional data in budget document | 2017 | continuosly during the programme | MoF | budget users |  |  | Continuously realized. Public debate was held for the first time, at which the 2018 Draft Budget was presented. 2018 Budget: tables on the State Budget are supplemented with additional information (primary budget balance, memorandum, % difference), chart on expenditures by functional areas, amounts are quantified as regards the new initiatives and measures of the Government.
|  |  | Additional data in Final Account of the Budget | 2018 | continuosly during the programme | MoF | budget users |  |  | Annual Budget Account is in the process of preparation.
|  |  | Additional data in Fiscal strategy | 2017 | continuosly during the programme | MoF | budget users |  |  | Continuously realized. 2018-2020 Fiscal Strategy - fiscal data tables included, expanded narrative part, new tables and charts on local government budget, part on fiscal risks, additional data on component financed with IPA funds. 2018-2020 Fiscal Strategy, i.e. the section on public debt management policies, contains, for the first time, analysis on alternative borrowing scenarios, i.e. quantitative analysis by using MTDS (Medium-Term Debt Strategy) analytical tool developed by the World Bank and IMF.
|  |  | Additional data published on the MoF web site | 2017 | continuosly during the programme | MoF |  |  |  | Realized and will be realized continupusly. Reports on budget execution by budget user on monthly basis; reports on budget execution as regards the budget of the municipalities on quarterly basis; quarterly report on budget execution as regards the general government; semi-annual report on state budget execution, supplemented with detailed data on all budget users and macroeconomic review; legal amendments introducing the obligation for all budget users and public enterprises to publish their annual accounts on their web-sites and to be accessible to the public; obligation for the budget users and the public enterprises to publish all public contracts and annexes on the Electronic System for Public Procurement - e-procurement, thus being accessible to the public, data in the IMF 2013 - 2016 Annual Book are published, in line with the IMF GFSM 2014 Methodology.
|  |  | Fiscal transparency evaluation- IMF Mission | first half of 2018 | end 2018 | MoF and other relevant institutions | IMF |  |  | IMF Mission on Fiscal Transparency commenced on 30 April and ended on 14 May 2018.
|  | P5M1A2 | Publishing of Citizen's Budget | Q4 2017 Q4 2018 Q4 2019 Q4 2020 Q4 2021 | Q4 2017 Q4 2018 Q4 2019 Q4 2020 Q4 2021 |  |  | Publishing of Citizen's Budget | Citizen’s Budget published | Citizen's Budget was published, as per the modifications and amendments to the 2017 Budget and the 2018 Budget, on the web-site of the Ministry of Finance. This activity will be realized continuously.
|  |  | Preparation and design of the document | 2017 | continuosly during the programme | MoF
|  |  | Prepare all procedures for producing and printing the document | 2018 | continuosly during the programme | MoF
|  |  | Publishing the document Citizen’s Budget for 2018 published on the Ministry of finance web site | 2017 | continuosly during the programme | MoF |  |  |  | 2018 Citizen's Budget published on the web-site of the Ministry of Finance.
P6 Internal Control
P6M1 Improved PIC (FMC and IA) legislation and methodological framework
|  | P6M1A1 | Preparing the new PIC legislation | Q1 2018 | Q4 2020 |  |  | a) New PIC Law b) New rulebooks for FMC c) New rulebooks for IA d) New FMC Manual e) New IA Manual | a) PIC Law prepared and adopted b) / c) / d) / e) /
|  |  | Establishing of working group (WG) | Q4 2017 | Q4 2017 | MoF | MISA, GS, SIGMA |  |  | Working Group for for preparation of PIFC Policy is established and it will be also engaged in the preparation of the Law on the System for Internal Financial Control in the Public Sector. Draft 2018-2020 PIFC Policy is submitted to the DEU, and it will be submitted to the EC by the end of May. Modifications and amendments to the Law on Financial Inspection in the Public Sector will undergo parliamentary procedure by the end of June.
|  |  | Analysis of the existing legislation | Q1 2018 | Q1 2018 | MoF | CHU,WG and RESPA experts |  |  | Realized. Analysis was carried out with RESPA expert assistance.
|  |  | Drafting PIC law based on recommendation from the analyses conducted | Q2 2018 | Q2 2018 | MoF | CHU, RESPA experts |  |  | RESPA experts prepared new working version of the Law to be the basis for the work of the twinning experts who are to prepare the draft Law in Q3. Twinning Project is in the tendering stage by DEU.
|  |  | Public discussion on Draft PIC law | Q2 2018 | Q2 2018 | MoF | CHU, other stakeholders |  |  | Will be implemented in Q3. This activity is related with the previous activity.
|  |  | Preparation of final Draft PIC law and submission to the government for adoption | Q2 2018 | Q2 2018 | MoF | CHU, Government |  |  | Will be implemented in Q3. This activity is related with the previous two activites.
|  |  | Adoption of the PIC law by the Parliament | Q3 2018 | Q4 2018 | MoF | Government, Parliament |  |  | Will be implemented in Q4.
P6M2 Strengthened administrative capacities on central and local level on FMC and IA
|  | P6M2A2 | Establishing system for supervision of IA and FMC units | Q1 2018 | Q4 2021 |  |  | a) Increased human capacities of the Unit for supervision b) Training of the staff c) Implemented supervisions on FMC and IA units | a) Unit for supervision staffed b) Training of the staff of the Unit for supervision conducted c) /
|  |  | Start of the procedure for new recruitment in the Unit for supervision | Q4 2018 | Q1 2019 | MoF
P7 External Control and Parliamentary Oversight
P7M1 Improved strategic planning and external audit process in line with the ISSAIs
|  | P7M1A1 | Development and implementation of Strategic Plan of SAO | Q4 2017 | Q3 2019 |  |  | a) Assessment Report on improvement of audit process as per ISSAI b) Strategic audit planning process in line with SAO priorities and resources available c) SAO staff trained in strategic planning of audit | a) Assessment Report including recommendations on improvement of audit process as per ISSAIs elaborated b) Report with comparative analysis, recommendations and proposals with reference to the strategic planning process developed c) Up to 30 SAO staff trained in strategic planning
|  |  | Assessment on improvement of audit process as per ISSAI in view of strategic audit planning process | Q1 2018 | Q4 2018 | SAO | No |  |  | The activities for preparing Assessment Report, including recommendations for improving the audit process in line with ISSAIs, are ongoing. Within the Twinning Project on "Further improvement of administrative capacities and external audit efficiency of SAO" implemented in cooperation with the twinning partners - SAIs of Bulgaria and Croatia, two missions have been completed out of nine planned until the end of 2018. During the first mission (5 - 9 March 2018), a list of methodology documents for audit processes to be subject of ISSAI Compliance Assessment was drafted; during the second mission (16 - 19 April 2018), experience was exchanged on regularity audit (financial and compliance audit) through presentation of audit files.
|  |  | Comparative analysis, recommendations and proposals with reference to the strategic audit planning process | Q2 2018 | Q4 2018 | SAO | No |  |  | The activities for preparing Report with comparative analysis, recommendations and suggestions with reference to the developed strategic planning process in accordance with the Twinning Project on "Further improvement of administrative capacities and external audit efficiency of SAO", are planned for the period June-November 2018.
|  |  | Training of SAO staff in strategic audit planning | Q3 2018 | Q4 2018 | SAO | No |  |  | The activities for training on strategic planning for up to 30 SAO employees in accordance with the Twinning Project on "Further improvement of administrative capacities and external audit efficiency of SAO" are planned for the period September-December 2018.
|  | P7M1A2 | Assessment of institutional and human resources capacity of SAO in order to maintain high quality of audits, in accordance with the relevant legal framework | Q4 2017 | Q3 2019 |  |  | Report with recommendations on improving the institutional and human resources capacity of SAO in order to maintain high quality of audits | Report with recommendations on improving the institutional and human resources capacity of SAO
|  |  | Review with recommendations on improving of SAO’s institutional and human resources | Q3 2018 | Q4 2018 | SAO | No |  |  | The activities for drafting report with recommendations for strengthening institutional capacity and HR capacities in SAO in accordance with the Twinning Project on "Further improvement of administrative capacities and external audit efficiency of SAO" are planned for in the period July - December 2018.
|  | P7M1A3 | Improved administrative capacity for performance audit | Q4 2017 | Q3 2019 |  |  | a) Training of SAO staff in performance audit and audit of EU funds b) Audit Reports on performance audits conducted in the areas such as EU funds, ICT, public financial internal control, public procurement | /
|  |  | Training of SAO staff in performance audit and audit of EU funds | Q2 2018 | Q3 2019 | SAO | No |  |  | The activities for training of SAO employees on performance audit and audit of EU funds are ongoing. Within the Twinning Project on "Further improvement of administrative capacities and external audit efficiency of SAO", implemented in cooperation with the twinning partners - SAIs of Bulgaria and Croatia, two trainings on performance audit and audit of EU funds were organized and another two trainings are planned to be delivered in June 2018. The first performance audit training - General concept and audit planning phase - was organized from 11 to 13 April 2018 for 22 SAO auditors, and the second training on audit of EU funds - General concept, EU regulations for IPA II and ESIF and audit planning phase - was carried out from 25 to 27 April 2018 for 22 SAO auditors.
|  |  | Pilot performance audits conducted in the areas such as EU funds, ICT, public financial internal control, public procurement | Q3 2018 | Q3 2019 | SAO | No |  |  | The activities for pilot performance audits in the area of ​​EU funds, ICT, public internal financial control and public procurement within the Twinning Project on "Further improvement of administrative capacities and external audit efficiency of SAO", are planned for the period September 2018 - September 2019.
P7M2 Improved scrutiny over the budget by the Parliament
|  | P7M2A1 | Analysis of existing legal and institutional framework in regard to mutual cooperation between SAO and Parliament benchmarked to SAO-Parliament cooperation best practices in EU | Q4 2017 | Q3 2019 |  |  | Report with recommendations for improved transparency of the legislative scrutiny function of the Parliament based on implementation of EU best practices including options for processing and discussion of the audit reports within the parliament procedures. | Analysis of existing legal and institutional framework and practices in dealing with cooperation between SAO and Parliament benchmarked to best practices in EU performed
|  |  | To analyse the existing legal and institutional framework in the beneficiary country in regard to mutual cooperation between SAO and Parliament benchmarked to SAO-Parliament cooperation best practices in EU | Q1 2018 | Q4 2018 | Assembly | SAO |  |  | The activities for making analysis of the existing legal and institutional framework regarding mutual cooperation between SAO and the Parliament in comparison with EU best practice are ongoing. Within the Twinning Project on "Further improvement of administrative capacities and external audit efficiency of SAO", one mission and one study visit have been completed so far, and another mission is planned until the end of 2018. During the first mission (26 February - 2 March 2018), the existing legal and institutional framework on SAO cooperation with the Parliament of the Republic of Macedonia was analyzed. Within the study visit organized from 23-26 April 2018 in Zagreb, Croatia, representatives of SAO and the Parliament of the Republic of Macedonia had the opportunity to exchange experience with their Croatian counterparts and attend a session in the Croatian Parliament, where Croatia SAO audit reports were reviewed. The first mission and the study visit were realized with support and active participation of representatives from the Parliament of the Republic of Macedonia.