REPUBLIC OF NORTH MACEDONIA

MINISTRY OF FINANCE

Draft

Annual Monitoring Report on Implementation of Public Financial Management Reform Programme

for the period January - December 2024

January 2025, Skopje

Abbreviations and Acronyms

| AMS | Audit management system |
| --- | --- |
| CA | Customs Administration |
| CARNM | Customs Administration of the Republic of North Macedonia |
| CEF | Center of Excellence in Finance |
| CIPFA | Chartered Institute of Public Finance and Accountancy |
| CHU | Central Harmonisation Unit |
| DBRNM | Development Bank of the Republic of North Macedonia |
| EUROSAI | European Organization of Supreme Audit Institutions |
| ESPEO | Electronic System for reporting and recording obligations |
| ERP | Economic Reform Programme |
| EC | European Commission |
| ENER | Unique National Electronic Register of Regulations |
| EU | European Union |
| FAD | Fiscal Affairs Department |
| GAP | Growth Acceleration Plan |
| HR | Human Resource |
| IPA | Instrument for Pre-Accession Assistance |
| IFES | International Foundation for Election Systems |
| IFMIS | Integrated Financial Management Information System |
| IFIs | International Financial Institution |
| IMF | International Monetary Fund |
| INTOSAI | International Organization of Supreme Audit Institution |
| IT | Information Technology |
| ITE | Integrated Tariff Environment |
| ITIS | Integrated Tax Information System |
| ICT | Internal Customers Technology |
| MASA | Macedonian Academy of Sciences and Art |
| MoF | Ministry of Finance |
| ME | Ministry of Economy |
| MISA | Ministry of Information Society and Administration |
| MJ | Ministry of Justice |
| MASP | Multi-Annual Strategic Plan |
| NAO | National Audit Institution |
| NBRNM | National Bank of the Republic of North Macedonia |
| NDI | National Institute for Democracy |
| NPAA | National Programme for Adoption of the Acquis |
| OECD | Organisation for Economic Cooperation and Development |
| OBL | Organic Budget Law |
| PFM | Public Finance Management |
| PRO | Public Revenue Office |
| PPB | Public Procurement Bureau |
| PFA | Public Finance Academy |
| PPP | Public-Private Partnership |
| PAR | Public Administration Reform |
| PEFA | Public Expenditure Financial Accountability |
| PIM | Public Investment Management |
| RIA | Regulatory Impact Assessment |
| SWG | Sector Working Group |
| SAO | State Audit Office |
| SACPP | State Appeal Commission for Public Procurement |
| SMART | Specific Measurable Achievable Relevant Time-Based |
| SIGMA | Support for Improvement in Governance and Management |
| SESPPP | Single Electronic System for Public Private Partnership |
| SEA | Secretariat for European Affairs |
| SECO | Swiss State Secretariat for Economic Affairs |
| SAA | Stabilisation and Association Agreement |
| TA | Tax Administration |
| TSRS | Tax System Reform Strategy |
| UNDP | United Nations Development Programme |
| USAID | United States Agency for International Development |
| VAT | Value Added Tax |
| WB | World Bank |
| WFD | Westminster Foundation for Democracy |

Table of Contents

Introduction	5

1.	Background	6

2.	Links to Strategic Documents	11

2.1.	Policies, Strategies and Programmes Linked to PFM	11

2.2.	PFM Sub-Areas Strategies	15

3.	Links to External Assessments	22

4.	Development Partners Coordination	23

5.	Human, IT and Financial Resources - Administrative Capacities	27

6.	Summary of the Progress Achieved in the Implementation of the Programme during the Reporting Period	28

Pillar I - Economic Analysis, Macroeconomic and Fiscal Framework	28

Priority 1. Revenue Forecasting and Reporting	28

Priority 3. Strengthening Debt Management	31

Pillar II - Revenue Mobilisation	33

Priority 1: Tax and Customs Policy	33

Priority 2: Tax Administration	36

Priority 3: Customs	41

Pillar III - Planning and Budget	45

Priority 1: Budget Planning	45

Priority 2: Strengthened Public Investment Management	47

Priority 3: Effective Instruments under the Growth Acceleration Plan	48

Pillar IV - Public Procurement	49

Priority 1: Public Procurement Policy	49

Priority 2: Public Private Partnerships (PPPs)	51

Priority 3: Appeal Mechanism	51

Pillar V - Integrated Public Finances	52

Priority 1. Implementation of an Integrated Financial Management Information System (IFMIS) to Support the Implementation of PFM Reforms and Organic Budget Law	52

Priority 2: Strengthen the Accounting of Budgets and Budget Users	53

Priority 3: Public Finance Academy	54

Pillar VI - Public Internal Financial Control	55

Priority 1. Financial Management and Internal Control	55

Priority 2. Internal Audit	56

Priority 3. Financial Inspection	57

Pillar VII - External Control and Parliamentary Oversight	57

Priority 1. External Audit	57

Priority 2: Parliamentary Oversight	75

Pillar VIII - PFM at Local Level	77

Priority 1. Fiscal Decentralisation	77

Priority 2: Financial Discipline, Transparency and Accountability at Local Level	79

7.	Monitoring and Coordination	81

8.	Financing of the PFM Programme for 2024	83

Annexes	85

Annex 1: Monitoring matrix of the PFM Reform Programme for the year 2024	85

Annex 2: Risk assessment of the PFM Reform Programme for the year 2024	85

# Introduction

Monitoring Report on implementation for Implementation of the PFM Reform Programme for the period January-December 2024 was prepared by the Ministry of Finance (MoF) of the Republic of North Macedonia, with other line ministries represented on the Sector Working Group actively participating: Ministry of Economy and Labor, State Audit Office (SAO), Customs Administration of the Republic of North Macedonia (CARNM), Public Revenue Office (PRO), Public Procurement Bureau (PPB), State Appeal Commission for Public Procurement (SACPP). Process of Report preparation was initiated in the end of December 2024, and finalised by end-January 2025. The Report was prepared on the basis of an instruction for reporting, including deadlines and reporting templates, prepared by the IPA and NPAA Unit at the Ministry of Finance (Coordination Unit), facilitating the consolidation and the presentation of PFM reform reporting information.

It provides information on the progress achieved in implementing the reform activities for the period January – December 2024.

# Background

On 21st June 2022, Government of the Republic of North Macedonia adopted the 2022-2025 PFM Reform Programme and the 2022 Action Plan for Implementation of PFM Reform Programme.

2022-2025 PFRM Reform Programme (hereinafter referred to as: Programme) was a contination of the 2018-2021 Programme and resulted with a need to proceed with the reforms in this area. It is an ambitious effort covering all aspects of PFM: economic analysis, macroeconomic and fiscal framework, revenue mobilisation and collection, budget planning, public investment management, public procurement, including PPP, establishment of integrated financial management information system (IFMIS), Public Finance Academy, budget accounting, public internal financial control, external control and parliamentary oversight and PFM at local level.

Key goals of the Programme are improved fiscal framework, strengthened process of public finance planning, execution and reporting, increased revenue collection, strengthened public procurement system and improved internal and external control by increasing transparency and accountability in operations, which are to ensure accelerated and sustainable economic growth, higher living standard and better quality of life for the citizens. All this encompasses maintaining а stable budget in the long run, thereby continuing the rendering of quality and prompt services to the citizens and the businesses through modern and efficient public administration based on digitalisation. Further improvement of public financial management is necessary not only to underpin the measures aimed at fiscal consolidation and structural reforms, but also as a process which improves the quality of the public administration and ensures an attractive and desired environment for the investors. Moreover, the Government has developed sub-system reform strategies in the areas of public internal financial control and tax system.

What is important for the accession process is that PFM Reform Programme will support the EU dialogue and help in more efficient use of EU funds through the institutions of North Macedonia, on the road to EU accession. Sound public financial management is a key precondition in the process of EU integration and is linked to many negotiation chapters (Chapter 5 - Public Procurement, Chapter 16 - Taxation, Chapter 17 - Economic and Monetary Policy, Chapter 18 - Statistics, Chapter 29 - Customs Union, Chapter 32 - Financial Control and Chapter 33 - Financial and Budgetary Provisions).

Implementation of structural reforms through quality and sound economic policies in all spheres, above all fiscal policy with moderate fiscal deficit, but sustainable public debt for efficient, transparent and modern public financial management, is essential for a stable, sustainable development, boosted competitiveness of the Macedonian economy and achieving better economic results in future, as well as wellbeing of the citizens of the Republic of North Macedonia.

PFM Reform Programme envisages 8 pillars with 22 priorities:

Pillar I - Economic Analysis, Macroeconomic and Fiscal Framework

- Priority 1. Revenue Forecasting and Reporting

- Priority 2. Economic Analysis and Macroeconomic Forecasting

- Priority 3. Strengthening Debt Management

Pillar II - Revenue Mobilisation

- Priority 1. Tax and Customs Policy

- Priority 2. Tax Administration

- Priority 3. Customs

Pillar III - Planning and Budget

- Priority 1. Budget Planning

- Priority 2. Strengthened Public Investment Management

- Priority 3. Effective Instruments under the Growth Acceleration Plan

Pillar IV - Public Procurement

- Priority 1. Public Procurement Policy

- Priority 2. Public Private Partnerships (PPPs)

- Priority 3. Appeal Mechanism

Pillar V - Integrated Public Finances

- Priority 1. Implementation of an Integrated Financial Management Information System (IFMIS) to Support the Implementation of Public Financial Management Reforms and Organic Budget Law

- Priority 2. Strengthen the Accounting of Budgets and Budget Users

- Priority 3. Public Finance Academy

Pillar VI - Public Internal Financial Control

- Priority 1. Financial Management and Control

- Priority 2. Internal Audit

- Priority 3. Financial Inspection

Pillar VII - External Control and Parliamentary Oversight

- Priority 1. External Audit

- Priority 2. Parliamentary Oversight

Pillar VIII - PFM at Local Level

- Priority 1. Fiscal Decentralisation

- Priority 2: Financial Discipline, Transparency and Accountability at Local Level

The PFM Reform Programme 2022 - 2025 was subject to a mid-term review of objectives and indicators, which was carried out at the end of 2023, by OECD - SIGMA with EU support, which granted an extension of the Programme for 2 additional years, until 2027.

The draft - Public Finance Management Reform Programme for the period 2024 - 2027 was published on the website of the Ministry of Finance on 5 March 2024, in English. The public consultation was held in the form of a meeting of the PFM Working Group on 21 March 2024, with the participation of relevant stakeholders (donor community, civil society organizations, IFIs, local authorities and other stakeholders), in order to actively contribute to the process of determining and implementing reform priorities.

In April 2024, the Draft Public Finance Reform Program 2024-2027 with the Draft Action Plan for 2024 was submitted to the Government, but it was not adopted.

In addition, after the election process, the documents were harmonized with the Government Program 2024-2028, for which new documents were prepared, namely: Draft Public Finance Reform Program 2025 - 2028 with the Draft Action Plan for 2025. After the adoption of the documents by the Government and approval by the PFM Council, reports will be prepared on the status of implementation of the activities covered by the Action Plan for 2025.

The status of the implementation of the activities covered by the current PFM Proggrame for year 2024 is as follows: out of 92 activities, 24 are completed, 50 are in the process of implementation and 18 are not completed (not yet started), which in terms of the percentage of implemented activities is represented as follows:

Percentage of implemented activities in the reporting period from January - December 2024

The achievement of indicator targets at the measure level for 2024 is the following: out of 81 indicator targets at the measure level, 35 are achieved, 24 indicator targets are partially achieved and 22 are not achieved.

Percentage of achieved indicator targets at the measure level in the reporting period from January - December 2024

The achievement of indicator targets at the priority level for 2024 is the following: out of 33 indicator targets at the priority level 17 are achieved, 10 indicator targets are partially achieved and 6 are not achieved.

Percentage of achieved indicator targets at the priority level in the reporting period from January - December 2024

The detailed status of achievement of indicator targets for 2024 and status of implementation of the planned activities are presented in the Annex 1: Performance Indicators Matrix for PFM Reform Programme for the year 2024.

The updated Risk assessment for PFM Reform Programme for the year 2024 is presented in Annex 2.

# Links to Strategic Documents

National authorities continue to maintain close co-ordination of all PFM sub-systems’ strategies and policies, as well as with other relevant national strategies.

## Policies, Strategies and Programmes Linked to PFM

2022-2025 PFM Reform Programme takes into account all the relevant documents in the field of European integration, such as the Stabilisation and Association Agreement (SAA) between the European Communities and their Member States, on the one hand, and the Republic of North Macedonia, on the other hand, as well as all relevant national strategic documents in this area.

IPA III Strategic Response

Priorities set out in the PFM Reform Programme are in line with the priorities for EU financial assistance to support the Republic of North Macedonia on its path to EU accession for the period 2021 - 2027 set out in the IPA III Strategic Response.

In order to strengthen public finance system, promote transparency, accountability, fiscal discipline and efficiency when collecting, managing and using public resources, IPA plans to invest in implementing and upgrading the reform strategies to ensure fiscal sustainability and sound management of public finances as applicable in the EU, improving the capacity for domestic revenue mobilisation and effective management of public funds, through improving stability, efficiency, and quality of revenue collection system (tax system and policy and customs system), including introduction of green taxation, improving budget planning reliability, further supporting of the implementation of integrated information system for public financial management, public investment planning and management; strengthening the management of assets and liabilities; enhancing the policy-based fiscal strategy and budgeting, strengthening the public procurement through support in implementing an overall strategy for the development of the public procurement system, including aspects of innovative, green and social procurement, improving public private partnership for concessions, enhancing internal control, strengthening decentralised managerial accountability, strengthening the accounting and reporting, enhancing the external audit.

Economic Reform Programme (ERP)

Economic Reform Programme (ERP) 2024-2026 was submitted to European Commission (ЕЦ) on 17.02.2024. According to the EC assessment of the ERP 2024-2026, implementation of Joint conclusions adopted within the ECOFIN Dialogue with EC in May 2023, is assesses as “partialy”, with result of 55.6%.

If disaggregated by policy recommendations, for those related to macro-fiscal policy, as fully implemented are assessed those referring to adopted tax policies by the Parliament and managing the price pressure by the National Bank. Substantially implemented were those referring to support provided for citizens and companies for dealing with energy crisis and adopted Fiscal strategy foreseeing deficit decrease at level of 3% in 2026. Partial implementation was noted due to the need for strengthening the capacities of MoF Department for public investment management and still not adopted the bylaw regarding public investments appraisal and PPP Law, Fiscal council is not fully equipped with personal, the Law on National bank is not amended in manner excluding the employees of the NB as administrative servants. Limited progress is noted regarding the supplementary budget, as reallocations were made for increase in public administration wages, pensions, and to the health fund, on contrary to IMF recommendations to use unused allocation for Corridor8/10d.

Economic and Financial Dialogue related to ERP 2024-2026 that was held in Маy 2024. The recommendations refer to:  Implement the 2024 budget as adopted and ensure the fiscal target is met;  Strengthen the administrative capacity for the regular preparation and publication of the tax expenditure report and explore all options to further broaden the tax base; Introduce an integrated approach for reducing the build-up of arrears of public sector entities, through putting in place an Integrated Financial Management Information System and by setting up an effective system for monitoring of fiscal risks in the Ministry of Finance, including the fiscal risks stemming from SOEs and arrears; Ensure timely implementation of the new Organic Budget Law (OBL) in its entirety by 2025, by adopting the necessary by-laws; To improve public investment management, adopt a methodology/guidelines for appraisal of projects, in line with the recommendations of the IMF and the World Bank, and ensure sufficient training of staff in the new PIM department of the Ministry of Finance; adopt the Law on Public Private Partnership.

ERP 2025-2027, after being adopted by the Government, will be submitted to EC till 15th of January at latest, as per EC Guidance Note.

National Programme for Prevention of Corruption and Conflict of Interests 2021 - 2025

Achieving the objectives and implementing the measures under the Strategy should ensure increased confidence in the institutions of the system, efficient use of public resources and strengthening the democracy, social values and exercising of human rights.

The Strategy detects and selects priority issues that generate high risk of corruption and identifies measures to overcome them. Issues and measures envisaged by this Strategy systematised in the following areas: public procurement, public sector employment, political system, judiciary, law enforcement authorities, health, labour and social policy, urban and spatial planning, environment, agriculture, sports, economy and business, public enterprises, media and civil society.

Public Administration Reform (PAR) Strategy 2023-2030

Public administration reform is a central area of ​​the Cluster “Fundamentals” who is crucial for the progress in negotiations with the EU and therefore public administration reform remains one of the Government's key priorities. Given that the duration of negotiations for full membership depends on the speed with which reforms are implemented in the country, a new The Public Administration Reform Strategy (2023-2030) has been prepared, in the time period by which the Republic of North Macedonia is expected to become a full member of the EU the following vision is set: depoliticized, efficient, effective and accountable public administration that provides quality policies and easily accessible services for citizens and the business entities. The work of public administration is based on European principles and values ​​and contributes to sustainable economic growth, rule of law, social cohesion and well-being. The Public Administration Reform Strategy (2023-2030) with Action Plan 2023-2026 was adopted at the 166th session of the Government of the Republic of North Macedonia held on July 11, 2023. It was presented on September 20, 2023 at an event organized by the Ministry of Information Society and Administration (MISA) in cooperation with SIGMA where the new strategy, the development process and the mechanisms for implementation and monitoring, as well as the key goals and priorities until 2030 were presented by priority areas.

With the aim of presentation and discussion of the strategic priorities of the public administration reform sector and better coordination of donor support and national activities in this sector, on 05.07.2023, the MISA in cooperation with the Secretariat for European Affairs and the Project for "Support for Policy Reforms, Accession and Effectiveness" held a plenary meeting of the sector working group for PAR in the premises of the Government of the Republic of North Macedonia.

Public financial management reform is one of the key pillars of the public administration reform (PAR), accordingly being incorporated in the PAR Strategy and the Action Plan for Implementation of PAR Strategy. Given that modern public administration is basis for efficient and effective public financial management, when preparing the PFM Reform Programme and the PAR Strategy, full coherence and harmonisation of both strategic documents is ensured. Particular attention has been paid to the human resources capacity, policy planning capacity, e-services, provision of services and orientation towards results coordination as regards enhancing managerial accountability, internal control environment and improving transparency. Moreover, link between these two strategic documents has been further strengthened with the Minister of Information Society and Administration participating in the process of managing and coordinating the PFM Reform Programme, as a member of the PFM Council, and its representatives in the PFM Sector Working Group, thus ensuring consistency and complementarity in the implementation of both documents. Furthermore, PFM reforms are put on the agenda of the SAA monitoring process, in particular, the progress in implementation of the reforms is discussed during the meetings of the Special Group for Public Administration Reform. In addition, the agendas of the PFM policy dialogue and the Special Group for Public Administration Reform are harmonised. On 22.09.2023, the MISA and the Ministry of Finance in cooperation with SIGMA, organized a workshop to improve the coordination between public administration reforms and public finance management in North Macedonia. The workshop was meant for the key officials involved in monitoring the implementation of the PAR Strategy and the PFM Reform Programme.

On January 18, 2024, the Ministry of Information Society and Administration (MISA) held a training with the contact persons for public administration reform, as well as with the persons who were involved in the activities of the evaluation mission of SIGMA. At this training, an IT tool for monitoring the implementation of the Public Administration Reform Strategy was presented by an expert hired by ReSPA.

In January 2024, MISA, in cooperation with SIGMA organized two workshops for the implementation of the evaluation mission in accordance with the principles of public administration of SIGMA. One planned for the representatives of the relevant competent authorities who were included in the interdepartmental working group for the implementation of the evaluation mission.  While the other workshop was planned for the people who entered data into the information system of SIGMA needed for the evaluation mission.

On April 18, 2024, MISA organized a training for the persons in charge of entering data into the IT tool.  Consequently, the Annual Report on the implementation of the Action Plan of the Public Administration Reform Strategy 2023-2030 for 2023 has been prepared with the help of this tool.

In accordance with the amendments to the Law on Organization and Operation of State Administration Bodies (Official Gazette of the Republic of North Macedonia No. 121/24 of 10.06.2024), the Ministry of Information Society and Administration was transformed into the Ministry of Digital Transformation (MDT) and the Ministry of Public Administration (MPA) with competences determined by the same. Based on the mentioned legal amendments, the competences related to the coordination of the Public Administration Reform Strategy fall under the competence of the Ministry of Public Administration.

On 17.12.2024, the 13th meeting of the Public Administration Reform Special Group between the European Union and North Macedonia was held. The meeting was co-chaired for the European Union by a representative from Directorate General for Neighbourhood and Enlargement Negotiations of the European Commission, and for North Macedonia by representatives from the Ministry of Public Administration. The European Commission will additionally submit the conclusions of this meeting.

On 25.12.2024, the second session of the Secretariat for Public Administration Reform was held, which was the first in this composition, after the adoption of the last legal amendments and additions to the Law on Organization and Operation of State Administration Bodies.

# PFM Sub-Areas Strategies

Strategies developed under different PFM sub-systems are coordinated and consistent with the PFM Reform Programme.

Tax System Reform Strategy covers a 5-year period (2021 - 2025), adhering to the deadlines set in the other strategic documents of the Ministry and its bodies. The Strategy outlines five priorities (1 - Increased Fairness of Taxation, 2 – Improved Efficiency and Productivity of the Tax System, 3 – Increased Tax Transparency, 4 – Improved Quality of Services, 5 – Introduction of Green Taxation) for tax policy creators and tax authorities administering the tax revenues in the period 2021-2025, with associated key activities, deliverables, responsible entities and KPIs.

Strategy for Improvement of the Public Procurement System in the Republic of North Macedonia 2022 -2026

The Strategy for Improvement of the Public Procurement System in the Republic of North Macedonia 2022 -2026 is adopted by the GoRNM in March 2022.

The Strategy is comprehensive and brings together the activities of the key institutions in the public procurement system in the country i.e. Public Procurement Bureau, State Appeals Commission, State Audit Office, Commission for Protection of Competition, State Commission for Prevention of Corruption, and Ministry of Economy. It establishes several priority areas, including improvement of the legal, institutional framework and legal remedies, e - procurement, PPP, anticorruption measures, green, social aspects and innovation in procurement as well as strengthening of the administrative capacities and professional trainings for procurement officers.

The implementation of the Strategy is supported by annual action plans and it is monitored by Coordinating body, composed by representatives of all involved institutions and chaired by the Director of PPB. According to the Annual Monitoring Report for 2022, the realisation of the activities is 68%. The Annual Monitoring Report for 2023 and Annual Action Plan for 2025 are are prepared and will be submitted to the government for adoption.

The Strategic plan of the PRO for the period 2025-2027

The Strategic plan of the PRO for the period 2025-2027 the period 2025-2027 is in line with the PFM Program.

The main strategic priorities and objectives of the PRO in the period 2025 – 2027 are achieved through the following programs

PROGRAM 1: TAX ADMINISTRATION, Sub-program I. Strong administration-healthy condition, PROGRAM 2: TAXPAYERS, Sub-program I. Cooperatively towards a common goal, PROGRAM 3: TAX REVENUES, Sub-program I. Integrated compliance, Sub-program II. Consistently against non-compliance; PROGRAM 4: DIGITAL TRANSFORMATION, Sub-program I. Transition to the digital world. The plan contains activities that are fully consistent with the planned activities within Priority 2 – Tax Administration of the Program.

PRO Reform Program 2025 -2028 "Transition to the Digital World"

The goal of the program is, through the digitalization of all PRO functions, by applying modern information and communication technology and providing a reliable and secure information system, to transform the PRO into a flexible, efficient, effective, and service-oriented tax administration. The priorities of the Program are:

• Priority 1: Consolidated electronic tax administration (e-PRO);

• Priority 2: PRO analytical capacity platform; and

• Priority 3: Security, stability, and sustainability of ITIS.

Expected results of the Program are changes that should be achieved by the end of 2028, which will reorganize the PRO according to a new business - digitalized model:

• Calculation and payment of taxes integrated into the "natural environment" of taxpayers and simplified automated and paperless processes integrated with other state and public authorities and entities, financial institutions, and other relevant stakeholders;

• Enabled services for taxpayers and other stakeholders through various channels;

• Tax revenue management based on compliance, risk management and informed decision-making;

• Integrated information system of the PRO with fulfilled standards for security, stability and sustainability.

Strategy for risk management in the processes of the PRO 2023-2025

The purpose of this Strategy is to establish and maintain a functional system for achieving the strategic goals and regular work activities of the PRO through the management of processes that contribute to greater quality, efficiency and results in all activities and at all levels. This means that risk management remains an integral part of the annual planning process.

The purpose of this Strategy is to determine the risk management process in all phases, whereby it should enable:

- improving the efficiency of risk management at the level of the PRO,

- risk management to cover all areas of the work of the PRO,

- that risk management is an integral element in the planning and decision-making process as a standard,

- raising the degree of awareness of the risks of the employees of the PRO during management, assessment and action as well as during the performance of regular work tasks,

- coordinated approach to risk management in the organization, which will cover all areas of risk.

The strategy for the development of the Customs Administration of the Republic of North Macedonia for the period 2022-2024

The strategy has been drafted in accordance with the strategic determinations and priorities presented in the Work Program of the Government of the Republic of North Macedonia in the period 2020-2024 and the corresponding national strategies and programs in areas that have an impact on customs operations. When defining the strategic goals, the commitment of the European Union with tax and customs policies to provide support for economic recovery from the crisis with COVID-19, to raise customs administrations to a higher level of modernization, with advanced staffing that enables better protection, was also taken into account citizens and society through efficient and proactive action of the customs services. The vision of the Customs Administration is to be a leading Customs Administration in the region, recognized as a protector of borders and society and a strong supporter of the legal economy, as well as a modern and innovative customs service with fully applied European Union standards, through the four strategic priorities: 1) collection of income and protection of financial interests, 2) facilitation of trade, 3) protection of society and 4) organizational and infrastructure development. The strategy is fully in accordance with the Program through the objectives: 6.2.1 Harmonization of the national customs legislation with the legislation and best practices of the European Union; 6.2.2 Digitization of customs and excise procedures; 6.2.3 Modernization of the customs ICT infrastructure to support operations; 6.2.4 Trade facilitation through regional economic integration; 6.3.1 Suppression of illegal trade and organized crime; 6.3.3 Strengthening the area of ​​"bans and restrictions"; 6.4.1 Strengthening the human resources management system; 6.4.2 Implementation of measures to prevent inappropriate and corrupt behavior and development of rules and control systems. At this moment the drafting of a Strategy for the development of the Customs Administration of the Republic of North Macedonia for the period 2024-2026 is ongoing.

ICT development strategy in the Customs Administration for the period 2021 - 2025

In the period 2021 - 2025, the CA plans to implement several projects from all areas of customs operations, which should be supported by IT. Most of these projects are part of the preparation process for the accession of the Republic of North Macedonia to the European Union (EU). In the foundations of this strategy are the user requirements and goals that arise from the business strategy of the CA, and are aligned with the priorities and plans at the national and European level.

The goals that are expected to be achieved through the implementation of the Strategy are related to the digitization of customs operations through: 1. Interconnectivity and interoperability with EU ICT systems, 2. Implementation of integration standards with the National Platform for Interoperability, 3. Improvement of the ICT environment, 4. Application of modern technologies and practices for the implementation of business claims and 5. Promotion of the use of the Internet, intranet and social networks in customs operations.

Risk management strategy for customs matters 2023-2026

The need for efficient risk management in the international supply chain is of crucial importance for ensuring the safety and security of the population, protecting the financial and economic interests of the country, and at the same time facilitating legal trade.  In May 2023, the Risk management strategy for customs matters 2023-2026 and the Action Plan for its implementation were adopted. The strategy covers the key objectives for dealing with risks that may arise in relation to customs issues, with the main goal of achieving a: quality, comprehensiveness, effectiveness and efficient approach to risk management. The strategy establishes the main strategic priorities: 1. Strengthening the capacity of employees for risk management; 2. Improving the quality of data and IT support for efficient risk management; 3. Provision, availability and sharing of data for risk management, cooperation between institutions and international cooperation; 4. Effective control system based on risk management, pre-assessment, control where necessary and 5. Promotion of cooperation with the business community in order to facilitate and accelerate legal trade.

CEFTA Risk Management Strategy 2020-2024

The application of risk management within the framework of CEFTA has been expanded and improved, according to the CEFTA Risk Management Strategy 2020-2024 and systematic exchange of electronic data (SEED) to all agencies involved in the customs clearance of goods In the period January-June 2023, activities continued for the harmonization of the proposal decision to establish an electronic system to facilitate risk management in CEFTA, which would include common risk profiles in CEFTA, exchange of data from reports on performed controls and rapid alerts. The activities for establishing the exchange of information through the SEED system for the CEFTA parties that do not border each other also continued.

Strategy for integrity and fight against corruption in the Customs Administration of the Republic of North Macedonia 2023-2026

A new draft text of the Strategy has been prepared being in line with the Arusha Declaration of the World Customs Organization, and the Decisions of the Government from the 50th session, as well as from the 69th session in 2021. The strategy for integrity and fight against corruption of the Customs Administration aims to strengthen the systems of prevention and repression of corruption and conflict of interests, defining the directions for strengthening the capacities and independence of the institution in the implementation of legal powers through the development of the concept of integrity. The strategy is based on 19 elements, which are also activities essential for integrity and the suppression of corruption.

SAO Development Strategy 2023-2027

With the aim to update SAO strategic objectives and to adapt operation to the current state of affairs and challenges in the society, new strategy was prepared and adopted. Priorities and Measures within Pillar 7: External control and parliamentary oversight of 2022-2025 PFM Reform Programme are closely related to the strategic objectives contained in SAO Development Strategy for 2023-2027.

In this Strategy, SAO has set the key priorities and goals, identified through the following strategic objectives:

- Ensuring and maintaining full State Audit Office independence

- Further maintenance of internal management capacities, institutional support, endeavors for continuous improvements, relations with stakeholders/ communication, human capacities, audit methodology

- Delivery of measurable results from performed state audit, performing high quality audits, audits of public interest and increase of public trust aimed at improving the lives of the citizens

- Creation of strategic plan for defining potential audit areas by assessing challenges in the areas of interest and in line with the risk assessment for the period 2023 – 2027.

SAO Communication Strategy 2024-2027

The Communication Strategy 2020 - 2023 was upgraded with the new Communication Strategy for the period 2024 - 2027, which provides for constant communication to motivate and make possible deeper and comprehensive, strategically based involvement of target groups from the civil domain to strengthen the effect of SAO findings and recommendations. The Communication Strategy is in line with PFM Reform Program and SAO Development Strategy 2023-2027. The key objective of the Communication Strategy is to increase the level of awareness of the wider public about SAO function and task and to strengthen SAO role as an institution serving the public. The Strategy defines specific objectives aimed at achieving specific results, which are directly related to SAO strategic activities as follows:

- to encourage SAO role as promoter of the principle of transparency and accountability of public funds;

- to develop and strengthen cooperation and coordination with all interest groups;

- to set up public support for SAO work and to ensure public participation;

- to encourage institutions to act upon SAO reports through greater engagement of the public.

For increasing transparency and accountability, as well as availability of information on SAO operation and on the shortcomings contained in the final audit reports, SAO has put together a register of 1.215 stakeholders. SAO has also continued with the practice of preparing audit abstract and press release for the public, where key shortcomings / information contained in final audit report are presented in a simple and comprehensible way. SCOPE OF THE STRATEGY AUDITEES INTOSAI & EUROSAI AUDIT AUTHORITY FOR AUDIT OF IPA When publishing final audit reports on SAO website (www.dzr.mk), the information is also sent to all stakeholders and posted to SAO Facebook page (https://www.facebook.com/DrzavenZavodzaRevizija).

Aimed at increasing transparency and accountability in SAO operations and making available information on SAO operations and shortcomings contained in final audit reports, SAO compiled a register of stakeholders, which currently contains 1.113 stakeholders. For this purpose, SAO created an audit abstract and press release that contain key shortcomings / information from final audit reports presented in a comprehensible way. When final audit report is published, the information is shared with all stakeholders. Information about SAO operation and final audit reports is published on SAO website (www.dzr.mk) and FB page (https://www.facebook.com/DrzavenZavodzaRevizija).

For maintaining continuity of SAO communication with stakeholders and ensuring continuous growth of SAO transparency, accountability and responsibility in SAO operation as well as informing citizens about audit enties operations.

SAO Strategic Audit Plan 2024-2027

The Strategic Audit Plan of the State Audit Office for 2024-2027 is corresponding with the PFM Reform Program 2022-2025. Measures within Priority 1: External audit, are in full compliance with point 2, strategic objectives and priorities of SAO audit departments, which include supervision over the spending of public funds, quality financial reporting, fight against corruption, continuous increase of responsibility and accountability and transparency etc.

Human Resource Management Strategy 2024 – 2027

The Strategy for Human Resources Management 2024-2027 is in line with SAO Development Strategy 2023-2027 and the PFM Reform Program 2022-2025. Namely, strategic objective 2 – Motivation and training of SAO employees and strategic objective 7 – communication, are closely related to priority 1: External audit, measures 1: Strengthening legal framework for external audit and measure 2: Strengthening SAO institutional and HR capacities. Increasing knowledge and skills of SAO employees is one of the main commitments of the institution, and these commitments are implemented through the Annual Plan for continuous professional development.

IT Strategy 2023-2027

SAO IT strategy for the period 2023 - 2027 is the basis for implementation and development of SAO IT systems. The IT Strategy is in line with SAO Development Strategy 2023-2027 and with Priority 1: External Audit, Measure 1: Strengthening legal framework for external audit and Measure 2: Strengthening SAO institutional and HR capacities from the PFM Reform Program 2022-2025, given that they are closely related to strategic objective 1: providing and maintaining necessary resources for continuous development of SAO IT systems and strategic objective 4: presenting results of SAO operation of SAO from the IT strategy.

# Links to External Assessments

In 2024, OECD/SIGMA, with financial assistance from the European Union, conducted an assessment of how the Republic of North Macedonia is performing against the standards set by the Principles of Public Administration. The final report was submitted to the Ministry of Finance on 20 December 2024. This report covers the six thematic areas of public administration (strategy, policy development and coordination, public service and human resource management, organization, accountability and oversight, service delivery and digitalization, and public financial management) and provides indicator values ​​and a comparison of overall trends across public administration.

# Development Partners Coordination

Development partners remain committed to supporting PFM reforms and maintain policy dialogues in the country with the PFM Reform Programme 2022 -2025 as well. Therefore, in order to ensure good planning and complementarity of external technical support, proper sequencing and successful implementation of the reforms, the MoF will continue coordinating the development partners’ assistance by conducting an open and inclusive PFM policy dialogue with all relevant institutions.

Monitoring the PFM Reform Programme 2022 -2025 is based on sectoral dialogue, introduced with the previous PFM Reform Programme, with all stakeholders - external partners.

In 2024, the following documents were prepared: Revised Draft PFM Reform Program for the period 2024-2027 (with Draft Action Plan for 2024) and the Draft Report on Monitoring the implementation of the Action Plan for 2023 for the PFM Reform Progrmme, for the period January - December 2023 were published on the website of the Ministry of Finance on March 5, 2024 for public consultation with members and observers from civil society organisations and development partners, who participate in the SWG for PFM, as well as other stakeholders.

On March 21, 2023 a meeting was held with the SWG for PFM to discuss these documents.

In April 2024, the Draft PFM Reform Program 2024-2027 (with an Action Plan for 2024) was submitted to the Government, but it was not adopted. Additionally, on 27 August 2024, the Government adopted the Draft Report on Monitoring the Implementation of the Action Plan for 2023 for the Public Finance Management Reform Program, for the period January - December 2023, after prior approval by the PFM Council.

On September 21, 2023, a meeting was held with the SWG for PFM to discuss progress in the implementation of the 2023 Action Plan for the PFM Reform Programme for the period January - June 2023. Before the meeting, the Draft Report on September 12, 2023 was published on the website of the Ministry of Finance for public consultation with stakeholders.

Starting from the beginning of 2020, the Ministry of Finance, in cooperation with other institutions (PRO, Customs Administration, PPB, State Appeal Commission for Public Procurement and Ministry of Economy) implement two major twinning projects financed under EU - IPA 2018, which are to provide support to MoF’s functions in the field of budget planning and execution, internal control, public procurement, as well as tax and customs policy and system and revenue collection:

PFM development partners’ coordination is carried out on the following two levels:

Policy level - PFM Council and PAR Council. One of the main tasks of the PFM Council is to facilitate the policy dialogue with the relevant institutions and development partners. PFM Council members participate in the PFM Policy Dialogues with all relevant stakeholders.

Technical level - PFM Sector Working Group - directly related to the working groups established for development and monitoring of the PFM sub-system strategies and policy papers. Also, separate development partners coordination meetings on operational level are organised with regard to the implementation of specific PFM sub-area measures.

- Strengthening budget planning, execution and internal control functions, with the following EU Member States as twinning partner: The Netherlands (National Academy of Economics and Finance of the Ministry of Finance), Croatia (Ministry of Finance), Latvia (Ministry of Finance) and Bulgaria (Ministry of Finance). The Project commenced in February 2020 and ended on July 31, 2024, with a planned duration of 54 months. A closing conference for the project was held on July 3.

- Improving revenue collection and tax and customs policy, with the following EU Member States as twinning partner: Austria (Agency for European Integration and Economic Development together with the Federal Ministry of Finance) and Croatia (Ministry of Finance - Customs and Tax Administration). The project was suspended, then canceled and the activities planned to be implemented in 2022 did not start/continued to be implemented.

Through the mediation of the USAID Project, a coordination group was formed with representatives from 9 institutions in order to make proposals for the improvement of the Law on Property Taxes and the Methodology for Assessing the Market Value of Property. With technical assistance from USAID, a comparative analysis and proposed scenarios for the model for the transformation of the Bureau for Regional Development into the Agency for Regional and Local Development have been prepared.

UNICEF and the World Bank need an analysis of the criteria for the allocation of the primary education block, while with technical support from SIGMA, the criteria for the allocation of the culture block have been analyzed.

With the assistance of UNDP, a comparative analysis has been prepared with some of the neighboring countries and EU member states for the distribution of capital transfers and proposed criteria for the distribution of capital grants, and also with the support of UNDP, financial indicators from the periodic financial reports of the municipalities are published on the websites of the municipalities and the website of the Ministry of Finance.

For finances, financial indicators are published in the periodic financial reports of the general parties.

IMF FAD technical assistance for the tax administration of North Macedonia is crucial for successful implementation of the foreseen strategic priorities, measures and activities. Furthermore, IMF’s continuous support to the long-term modernisation processes and the already developed reform programmes will greatly contribute to ensuring smooth change management to the end of establishing electronic tax administration and improving the public finance management – revenue mobilisation.

In order to acquaint the donors with the upcoming reforms in the Public Revenue office and to avoid overlapping donor aid, the Public Revenue Office with the technical support of the IMF held the first coordination meeting on May 4, 2023of donors and creditors involved in the reform of the Public revenue office. The meeting was also attended by representatives from the MoF, IMF, World Bank, EUD, UNDP, US Treasury and Finance Think.

The State Audit Office, the Westminster Foundation for Democracy (WFD) and UK Foreign, Commonwealth & Development Office continued in 2023 with the implementation of the signed Memorandum of Understanding, which provides support in the implementation of SAO Communication Strategy for 2020 - 2023, through the implementation of the project "Increasing accountability and transparency in North Macedonia through improved implementation of SAO recommendations". The activities relate to the implementation of the remaining two phases of the Project in line with the Communication Strategy of the SAO 2020-2023, focusing on the communication and cooperation of SAO with the competent institutions and non-governmental organizations.

In March 2022, the State Audit Office and the United Nations Development Program (UNDP) signed Memorandum of Understanding, which defines series of activities to be implemented in the next two years, including promotion and advancement of governance reform with public finances and external audit; conducting audit of financial statements prepared on accrual basis, value for money audit, audit of Sustainable Development Goals and audit of local self-government units; support for institutional and organizational development capacities in managing environmental management; strengthening transparency and accountability through digitization of processes and services.

In 2023, the State Audit Office and the United Nations Body for Gender Equality and Empowerment of Women - UN Women continued the implementation of the Memorandum of Understanding and Cooperation, with the aim of both parties cooperating in promoting the implementation of gender equality obligations in accordance with national laws and policies as well as international commitments and promote gender-responsive public funds management and accountability through systematic implementation of gender-responsive budgeting as a policy-making tool.

SAO and the International Foundation for Election Systems (IFES) in February 2023, signed the Memorandum for cooperation with aim of both parties cooperating of increasing effectiveness in the performance of audit functions, especially in relation to managing corruption risks, public relations, advancing digitalization through innovative tools and software solutions, and improved transparency and accountability of political financing.

Strengthening cooperation with the Assembly of the Republic of North Macedonia for reviewing audit reports, strengthening parliamentary oversight of the use of public funds, increased effectiveness of SAO work in performing regular auditing functions /management, experience in executive transitions, advancing digitalization through innovative tools and software solutions, and improved transparency and accountability are envisaged as areas for cooperation in the Memorandum of cooperation signed by SAO and Nacional Democratic institute (NDI) in May 2023.

To establish institutional cooperation of mutual interest, the State Audit Office and the Office of the Auditor General of Norway signed Memorandum of Understanding on 15 June 2022, and commenced a five-year cooperation for providing assistance for development of SAO institutional capacities based on the principles and standards for professionalization of the International Organization of Supreme Audit Institutions (INTOSAI) and the European Organization of Supreme Audit Institutions (EUROSAI). During 2023, several working meetings were held in the direction of the implementation of the Memorandum of cooperation, through the implementation of pilot performance audits, the exchange of experiences in the use of the audit management system (AMS) and the need to improve its application, as well as other areas of common interest. To strengthen its role in the fight against fraud and corruption, SAO introduced organizational changes by establishing new audit department for detecting fraud and corruption. Also, to respond to the challenges of using modern digital technology to support audit processes, to increase efficiency and effectiveness of audit work, as well as to present audit results using innovative solutions, SAO has set up "innovative laboratory" as a separate organizational unit. These new organizational changes are part of SAO new acts for organization and systematization, which were adopted at the end of 2022.

The State Audit Office, the Chartered Institute of Public Finance and Accountancy (CIPFA) and the Center of Excellence in Finance (CEF) from Slovenia signed Memoranda of Understanding on 29 June 2022, thus setting up a formal basis for continued cooperation on activities for advancing joint commitment for sound public finance management and good governance, as well as sharing best practice for improving skills and capacities of public institutions and officials.

# Human, IT and Financial Resources - Administrative Capacities

The issue of strengthening administrative capacities in relation to the implementation of the PFM Reform Programme is addressed at 3 levels:

- PAR Strategy and Action Plan give particular attention to human resources capacity, policy planning capacities, e-services, service delivery and orientation to results coordination as regards enhancing managerial accountability, internal control environment and improving transparency across the public administration.

- PFM Reform Programme envisages numerous measures and activities related to the development of administrative capacities and IT systems of all PFM institutions. Measures and activities under each priority are defined taking into consideration current HR capacities of the PFM institutions, but also separate activities for further capacity building based on future recruitment plans are proposed, as part of the reform process. Significant number of results in the Programme is related to capacity building of the PFM institutions through new employment, knowledge enhancement and skills development and upgrading, which will be achieved through various forms of technical support and trainings. This has the potential to attract, regenerate and develop motivated and engaged employees. Improvements in the business processes (in the area of taxation, customs, internal control, public procurement and other areas) will create space for professional development of the public servants, while the new integrated IT systems (for PRO and IFMIS for the MoF) are oriented towards a more prudent, sustainable and cost-effective management of the public administration and the public resources.

- Also, strategic plans at institutional level are developed on 3-year basis and they provide overview of the objectives and the tasks of each separate institution, the activities for achieving the respective goals, the effects and the expected results and the human and financial resources for their implementation. In addition, pursuant to the Law on Administrative Servants, all public institutions prepare annual training plans.

All gaps identified are tackled by the relevant existing training bodies established in the respective sector, as well as within the framework of the various donor projects currently implemented and planned.

PFM Reform Programme envisages that all priorities, measures and activities are being funded through two main sources: the state budget and the development partners’ funded capacity development projects or technical assistance. The Programme provides a synopsis of the known estimated costs at the time of preparing the document. In addition, each annual Action Plan presents an estimation of the costs implications and sources of funds needed to implement the planned activities.

The analysis of costs and benefits and the regulatory impact assessment (RIA), carried out within each strategic document, envisages relevant financial resources.

Progress in capacity building of PFM institutions is further elaborated under the status of implementation of specific activities planned in the Programme (Part 4. Assessment of 2023 Action Plan Implementation).

In addition to regular budget funding, significant support during the preparation and implementation of the Programme was provided by the European Commission (IPA projects, TAIEX, SIGMA). Support was also provided by the World Bank, IMF, OECD, as well as by various bilateral programmes.

# Summary of the Progress Achieved in the Implementation of the Programme during the Reporting Period

# Pillar I - Economic Analysis, Macroeconomic and Fiscal Framework

# Priority 1. Revenue Forecasting and Reporting

Measure 1: Improving tax and customs reporting in accordance with the EU best practices

Certain activities were carried out in the Public Revenue and Tax and Customs Policy Department regarding the review of the reports submitted on the previously accomplished mission in December 2023 by the International Monetary Fund, and the progress made so far regarding the measure was discussed. For the upcoming period, activities with the assistance of the IMF for signing protocols for data exchange with the relevant institutions and prepare reports on tax expenditures are planned.

Measure 2: Enhancing tax and customs modelling capacity

In January-December 2024, the World Bank conducted short trainings on models for:

- Forecasting revenues from alcohol excise duties

- Forecasting revenues from excise duties on tobacco products

- Short training on the Power BI tool for monitoring of revenue

The implementation of the trainings is aimed at improving the capacity to independently simulate the fiscal effects of different public policy scenarios in these areas. These activities are a continuation of the activities undertaken with the support of the World Bank in the previous reporting period, which relate to the trainings held on the application of the personal income tax, corporate income tax and value-added tax models that will continue during the period 2025-2028, in order to enable the full implementation of the tax models in the Ministry of Finance.

Full utilization of tax models will significantly improve the Ministry of finance’s tax revenue forecasting capabilities and serve as a valuable tool for evidence-based tax policy making and estimation of tax expenditures.

Priority 2. Economic Analysis and Macroeconomic Forecasting

Measure 1: Capacity building for economic analyses

In cooperation with the Swiss State Secretariat for Economic Affairs (SECO), the Project for Macroeconomic Planning and Management is being implemented through a modular approach. The first module was carried out in 2022 and 2023, the second module was implemented in 2024, and the continuation of the project is planned for the period 2025-2026 with the implementation of the third module. In 2024, the following four training sessions were held (one training in each quarter):

• From March 18 to March 22, 2024, an onsite training was held to deepen the analytical skills of employees regarding the interpretation of economic data and projections obtained by updating the macroeconomic model, as well as to review the steps used in building the real and fiscal sectors in the model for the Macedonian economy. Also, within this mission a meeting was held with relevant sectors within the Ministry of Finance (Budget and Funds Sector and Tax and Customs Policy Sector) to present the results obtained from the model and discuss them.

• From May 13 to May 17, 2024, an onsite training was held to introduce large investment projects into the model, as well as to develop a tool to assess their impact on GDP growth. Also, within this mission a meeting was held with the State Statistical Office (SSO) to present the results obtained from the model and discuss the methodology used by the SSO for calculating GDP and how data revisions are carried out.

• From October 28 to November 1, 2024, an onsite training was held to update the macroeconomic model using data from the new 2025 Budget, as well as to use case studies (with a special focus on migration and remittances from abroad).

• From December 16 to December 20, 2024, an onsite training was held to update the macroeconomic model using economic assumptions in the real and external sectors, as well as to review the steps used in building the monetary and financial sectors in the model for the Macedonian economy. Also, within this mission a meeting was held with the National Bank to present the model and discuss the assumptions used in the external sector, with a particular focus on remittances from abroad.

Measure 2: Developing new macroeconomic models

In cooperation with the World Bank, the following models were developed for the needs of the Sector for Economic Policy and Development: a model for short-term inflation forecasting and a model for short-term GDP forecasting. The inflation model is in use, while the GDP nowcasting model requires further adjustments, which depend on the quality of the data. In accordance with the need for improved macroeconomic forecasting, the development and training for the macro-structural model (MFMOD) is underway, with the first training sessions starting in late 2023. During 2024, the following additional workshops related to the development of this model were held:

• In the period 29.01.2024-02.02.2024, training was held at the Ministry of Finance where the macro-structural model for the country was additionally presented. The training covered the following: presentation of the model, explanation of mathematical concepts, principles for changing input in the model, basics of programming basic commands in E-views, updating the model's database, and setting up a basic scenario, as well as discussing the specifics of the Macedonian economy and their application in the model.

• During March 2024, several online meetings (Baseline scenario-follow up) were held, where the principles for updating the model's database and adjusting the model using assumptions and building a basic macroeconomic scenario were presented.

• During September 2024, several online workshops were held aimed at preparing projections using the macro-structural model.

Measure 3: Fiscal Risks

As part of the activities to strengthen the capacity for assessing fiscal risks, a working group was formed within the Ministry of Finance in January 2024 to determine, define, monitor, and report on fiscal risks. Additionally, two IMF missions were conducted in January and March 2024 to identify, assess, and report on fiscal risks. During the first mission (from January 25 to February 6, 2024), meetings were held with all relevant institutions. After the completion of the mission, the IMF prepared a report titled "Strengthening the Analysis and Reporting of Fiscal Risks," with recommendations for: 1/ improving the identification and analysis of key areas from which fiscal risks originate; 2/ strengthening the institutional framework for managing fiscal risks; 3/ enhancing transparency in reporting fiscal risks. Within these areas, short and medium term sub-activities were proposed for implementation. Furthermore, the fiscal risks section of the Fiscal Strategy 2025-2027 was improved including additional analyses on risks related to: public and state-owned enterprises, municipalities, public debt and unpaid liabilities, legal claims from the state, public investment implementation, and PPPs, as well as environmental risks. During the second IMF mission (from March 18 to 22, 2024), that focused on the analysis and identification of fiscal risks of public enterprises, Health Check Tool was developed to assess the financial vulnerability and risks arising from their operations. The objective of this mission was to improve the Ministry of Finance’s capacity to identify and analyze fiscal risks stemming from the operations of state-owned enterprises.

Measure 4: Establishment of a Fiscal Council

With the 2022 Budget Law, provisions for the establishment of a Fiscal Council were envisaged. According to the criteria set out in Article 11, paragraph 6, it was requested that MANU, NBRSM, and DZR propose members, after which the Assembly formed the Fiscal Council and elected the following members: academician Abdulmenaf Bejjeti, proposed by MANU; professor Marina Trpeska from the Faculty of Economics, proposed by SAO; and professor Gligor Bishev, a long-time banker and former vice-governor, proposed by NBRNM. In 2023 and 2024, support from the World Bank was secured to fully establish and operationalize the Fiscal Council, as well as support for building the capacities of the body for professional and administrative support. In this regard, a Working Rules and Statute of the Fiscal Council were prepared, as well as Work Programs for 2024 and 2025. With the support of Finance Think, a study titled "Fiscal Discipline and the Effectiveness of Fiscal Rules in North Macedonia: The Path to Sustainability" was prepared. A website was also created, where all the opinions and reports prepared by the Fiscal Council are published.

# Priority 3. Strengthening Debt Management

Measures 1: Reducing Operational Risks at Public Debt Management

For the purpose of reducing the operational risks, and by following the digitalisation trends of foreign payment operations, digitalised payments towards foreign creditors have started to be introduced, by introducing electronic banking with NBRNM, through which repayments to foreign creditors are being made. As regards activity “Number of external debt orders paid electronically”, the target has been achieved, envisaging 70% of the external debt orders to be paid electronically.

To the end of achieving the priority pertaining to strengthening public debt management capacities, Ministry of Finance needs to strengthen the public debt management capacities by employing, as well as training the existing staff. Hence, in the first half of 2023, 2 persons were engaged through the Temporary Employment Agency, thus the activity “Strengthening Public Debt Management Capacities” has been partially implemented. This activity was finalised through the realization of 2 job announcement.

However, during 2024, there was an outflow of citizens in the Public Debt Management Sector, and at the same time, there was no realization of new employment and there is a need to re-equip with new employment.

Measure 2: Increasing transparency of public debt

The Republic of North Macedonia acceded to the IMF's highest standard for statistical data dissemination - SDDS Plus in 2019, confirming the quality of the statistical system, and the Ministry of Finance had a 5-year transition period to align data with this standard. The fulfillment of the requirements of the SDDS Plus standard was realized at the beginning of 2024, when data on public debt were published in accordance with this standard.

Measure 3: Introducing New Debt Instruments

The introduction of new debt instruments, as an activity in the Public Finance Management Reform Program, was implemented during 2023.

Namely, оn 29th September 2023, the Ministry of Finance issued structural bonds, to provide financial resources for financing the due and unpaid obligations of the municipalities of Tetovo, Želino and Vinica, recorded in the Electronic System for reporting and recording obligations as of September 30, 2021.

The first auction of the development bond for citizens successfully completed at 13th of July 2023, given that the accepted amount reached Denar 1,448,030,000, which is twice as much as the amount offered under the respective Prospectus, amounting to Denar 600 million, and 1,283 citizens participated at the auction.

Оn the 07th of November 2023 where the same conditions were offered in the Prospectus including the amount, tenor, interest rate and 907 citizens participated at the auction, investing total of Denar 1,085,480,000.

The green bond is a financial instrument that the Ministry of Finance introduces in its portfolio as a new instrument, on 03rd of October 2023. Under the respective Prospectus, the amount offered and accepted was Denar 600 million, although the demand was nearly three times higher.

The funds invested in this green bond will be intended to finance the Energy Efficiency Fund at the Development Bank of the Republic of North Macedonia. The fund will use these assets to finance energy efficiency investments by approving loans, issuing guarantees, and approving grants.

# Pillar II - Revenue Mobilisation

# Priority 1: Tax and Customs Policy

Measure 1: Improved Revenue Legislation Framework, Harmonised with the EU Acquis

As regards the Activity for implementation of GAP analysis of the national legislative provisions (laws and bylaws and methodology) compared to the latest EU legislation and best practices, in the area of tax and customs legislation, no new activities were realized in the reporting period.

This considering the fact that this Activity was implemented with a support under EU-IPA 2018 “Improving Revenue Collection and Tax and Customs Policy” Twinning Project, which was canceled in December 2022.

Regarding Activity 2, which refers to preparation of new legal acts and/or amendments to the existing national tax and customs legislation (laws and bylaws) prepared on the basis of the existing EU acquis, following activities were implemented:

- Draft Law on Amendments on the Personal Income Tax Law entered into force (based on the recommendations given in the Report on the progress of the MK for 2022, as well as the recommendations from the Joint Conclusions of the Joint Dialogue with the Western Balkans and Turkey, and the draft conclusions of the last Subcommittees on Economic and Financial Affairs and Statistics and on Trade, Industry, Customs and Taxation);

- Law on Amendments to the Profit Tax Law* was adopted („Official Gazette of Republic of North Macedonia “, no. 199/23 of 25 September 2023)

- Law on Solidarity Tax* was adopted („Official Gazette of Republic of North Macedonia “, no. 199/23 of 25 September 2023);

- Rulebook on the form and content of the form of the tax balance for taxation with solidarity tax was adopted ("Official Gazette of the Republic of North Macedonia", no. 200/23 of 25 September 2023)

- Law on Amendments to the VAT Law was adopted („Official Gazette of Republic of North Macedonia “, no. 199/23 of 25 September 2023);

- Rulebook for the method of application and registration of a foreign person, the method of ruining the register of tax representatives, the form and content of the register of tax representatives, the form and content of the application for registration for the purposes of value added tax as well as the required documentation was adopted („Official Gazette of Republic of North Macedonia “, no. 286/23 of 29 December 2023);

- Decision for determining the goods and services that are subject to a preferential rate of value added tax was adopted („Official Gazette of Republic of North Macedonia“, no. 203 of 28 September 2023);

- Law on Amendments to the Law on Excise Duties was adopted („Official Gazette of Republic of North Macedonia “no. 209/23 of 5 October 2023);

- Decree amending the Decree on the Manner of Calculation of the Motor Vehicle Tax and on the Amounts for Calculation of the Motor Vehicle Tax was adopted („Official Gazette of Republic of North Macedonia “no. 220/23 of 19 October 2023);

- Draft Law on Amendments to the Law on Commodity Reserves, in shortened procedure has been prepared and it is in Parliamentary procedure;

- preparatory activities for draft new Customs Law commenced;

- preparatory activities for a new Decree for the implementation of the Customs Law commenced;

- Decree amending the Decree on the classification of certain goods in the Combined Nomenclature in accordance with the regulations of the European Commission (10th continuation) was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.25 of 6 February 2023;

- Decree amending the Decree on the classification of certain goods in the Combined Nomenclature in accordance with the regulations of the European Commission (11th continuation) was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.74 of 6 April 2023;

- Decree amending the Decree on the classification of certain goods in the Combined Nomenclature in accordance with the regulations of the European Commission (12th continuation) was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.166 of 4 August 2023;

- Decree amending the Decree on the classification of certain goods in the Combined Nomenclature in accordance with the regulations of the European Commission (13th continuation) was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.202 of 27 September 2023;

- Decree amending the Decree on the classification of certain goods in the Combined Nomenclature in accordance with the regulations of the European Commission (14th continuation) was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.275 of 22 December 2023 and

- Decision on harmonization and amendment to the Customs tariff for 2024 was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.260 of 11 December 2023.

- Rulebook on the method of taxation with excise duty on energy products and electricity was adopted, published in the "Official Gazette of the Republic of North Macedonia" no. 18 of 25 January 2024;

- Rulebook amending the Rulebook on the method of taxation with excise duty on energy products and electricity was adopted, published in the "Official Gazette of the Republic of North Macedonia" no. 87 of 16 April .2024;

- Law on Amendments to the Law on Excise Duties was adopted, published in the "Official Gazette of the Republic of North Macedonia" no. 265 of 24 December 2024;

- Decree amending the Decree on the classification of certain goods in the Combined Nomenclature in accordance with the regulations of the European Commission (15th continuation) was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.91 of 19 April 2023;

- Rulebook amending the Rulebook on the reward system for customs officers was adopted, published in the "Official Gazette of the Republic of North Macedonia" no. 133 of 24 June 2024;

- Decree amending the Decree on the classification of certain goods in the Combined Nomenclature in accordance with the regulations of the European Commission (16th continuation) was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.258 of 18 December 2024;

- Decision on harmonization and amendment to the Customs tariff for 2025 was adopted, published in the “Official Gazette of the Republic of North Macedonia” no.269 of 26 December 2024, and

- Program for the management, arrangement and maintenance of border crossing facilities for road traffic for 2024 has been adopted, published in the "Official Gazette of the Republic of North Macedonia" no. 106 of 20 May.2024.

In addition, and in order to continue the activities covered by this Measure, during March 2023, the Ministry of Finance submitted an initiative to the DEU in North Macedonia for the approval of a Twinning Light Project entitled "Further harmonization of the tax legislation with the EU Acquis, Improving Revenue Forecasting and Reporting". As of 31 December 2023, the Ministry of Finance has not yet received an official feedback regarding the acceptance of this initiative by the European Commission.

Rulebook on Implementation of Law on Value Added Tax was adopted ("Official Gazette of the Republic of North Macedonia", no. 18/24 of 25 January 2024 and no.19/24 of January 2024).

The Law on a minimum global corporate income tax has been adopted by the Parliament in December 2024. The Law is harmonized with Council Directive (EU) 2022/2523 of 14 December 2022 on ensuring a global minimum level of taxation for multinational enterprise groups and large-scale domestic groups in the Union OJ L 328, 22.12.2022.

# Priority 2: Tax Administration

In the part of Measure 1: Strengthen administrative capacity for better revenue collection and tax compliance following progress was achieved:

Working group – Project team established by Decision of the Director of the PRO in accordance with its task to introduce a Center of Excellence for inventory, assessment, seizure and sale of property for the purpose of tax collection, prepared project documentation that provides:

• Designing the model of operation of the Center of Excellence, the affiliation in the structure of the internal organization of the Public revenue office and the division of duties with UEC (Unit for Enforced Collection) in Regional office and LTO (Large tax office)

• Assessment of the necessary human resources in a Center of Excellence with appropriate professional qualifications

• Assessment of other conditions for the practical functioning of the Center of Excellence (accommodation space, software applications, etc.).

The proposed model refers to the introduction of a new centralized organizational unit in the PRO - Tax Enforcement Center.

The practical implementation of the Tax Enforcement Center is conditioned primarily by amendments to the acts on internal organization and systematization of jobs in the Tax Administration, in order to introduce the new organizational unit and to be able to start the recruitment of human resources through internal redeployments and new employments, public procurement etc. In the meantime, amendments to the Law on the Public Revenue office came into force, with which the PRO is obliged within six months, that is, by November 2023, to adopt new acts for the internal organization of the PRO. With this, the formal-legal introduction of the Tax Enforcement Center as a new organizational unit in the PRO will be combined with the overall changes – the new internal organization of the PRO, which will be followed by other activities for its practical implementation.

The Tax Enforcement Center in the proposal of the act for internal organization and systematization of jobs in the Public Revenue Office (which is in the process of obtaining consent from the MISA), is introduced as a Department for inventory, assessment, seizure and public sale of movable objects and real estate within the Sector for Collection and Debt Management in the General Directorate.  The Public Procurement Plan of the PRO for 2024 incorporates part of the budget needs for the implementation and launch of the centralized unit.

Activities continue regarding the preparation of a Register of Compliance Risks by Tax Type and a Plan for Improving Compliance in the Construction Sector, with the aim of combating the shadow economy and improving taxpayer compliance.

A challenge for the successful implementation of other activities is training in compliance risk management and developing analytical skills of existing employees in the EUR, as well as staffing the Compliance Risk Management Unit.

In the part of Measure 2: Digital transformation of the PRO with the establishment of an Integrated Tax Information System (ITIS) following progress was achieved:

The project "Building effective, transparent and accountable institutions for the management of public finances" became effective with the conclusion of an Agreement with the World Bank through which financial resources were provided for certain modules of the new integrated TIS of the PRO, namely:

- IT solutions for the modernization of taxpayer services by improving the e-Taxes/e-Services portal and additional online opportunities to support citizen engagement in the tax domain through feedback mechanisms, smart applications or other software tools

- Data Warehousing and Business Intelligence Tools - Software and hardware required for the new DW for online analytical processing, statistics and reporting and software required for the development of compliance risk management tools and the PRO decision-making process

- Combined Call Center/Help Desk - Software and hardware required to set up a Call Center/Help Desk

- Hardware required for the implementation of the TIS modules - Procurement and installation of additional servers, data storage units, replication systems and other solutions required for the implementation of the TIS modules (including the e-invoicing module), expanding the operations of TIS in the existing PRO data center and the new joint DRC managed by the Ministry of Interior.

- The contract for the development of functional requirements and technical specifications for these modules has been signed. The duration of the contract is 18 months: 14.03.2024 - 14.09.2025, the Kick-off meeting was held on 19.03.2024 and it is being implemented smoothly.

- In addition, work is underway with the World Bank to finalize a Terms of Reference (TOR) document with the necessary technical assistance for the following functional areas:

• Support for the implementation of compliance risk management.

• Strengthening administrative capacities in functional areas

• Building the capacities of the Large Taxpayers Office (LTO).

With the amendments to the Law on the Public Revenue Office, which are in force from 03.05.2023 the formal organization and structure for the implementation of the digital transformation reform of the PRO has been arranged and accordance with the legal provisions, the Director of the Public Revenue Office with a decision dated 18. 05.2023 established a Working Body for the implementation of a tax information system, whose task is: implementation, upgrading, optimization, execution, regulation, maintenance, control, staff education and analysis of all processes and functionalities related to the tax information system.

In order to ensure the reliable realization of the project for the establishment of a new TIS, the Working Body prepared a reform program - a program for the implementation of the TIS and for the purpose of more effective monitoring of the implementation, it established a Reform Committee.

On 30.10.2024, the Public Revenue Office adopted the PRO Reform Program 2025 -2028 entitled "Transition to the Digital World". The goal of the program is, by digitizing all PRO functions, applying modern information and communication technology and providing a reliable and secure information system, to transform the PRO into a flexible, efficient, effective and service-oriented tax administration. The priorities of the Program are:

• Priority 1: Consolidated electronic tax administration (e-PRO);

• Priority 2: PRO analytical capacity platform; and

• Priority 3: Security, stability and sustainability of DIS.

Expected results of the Program are changes that should be achieved by the end of 2028, which will reorganize the PRO according to a new business - digitalized model:

• Calculation and payment of taxes integrated into the "natural environment" of taxpayers and simplified automated and paperless processes integrated with other state and public authorities and entities, financial institutions and other relevant stakeholders;

• Enabled services for taxpayers and other stakeholders through various channels;

• Tax revenue management based on compliance, risk management and informed decision-making;

• Integrated information system of the PRO with fulfilled standards for security, stability and sustainability.

With changes to systematization during 2024, conditions have been created for the formalization of the management structure, a Reform Management Unit has been established and staffed, and a new Committee for Strategic and Reform Management in the PRO has been established, consisting of the PRO Director and top tax officials.

The reform program envisages that the existing Working Body for the Implementation of DIS and the Reform Management Unit will be transformed into a permanent organizational unit - the Directorate for Digital Transformation, which will be composed of 3 sectors dedicated to the daily management of reforms and digitalization of processes in the PRO, namely:

• business processes and regulation in the Transformation Sector;

• digitalization in the Digitalization Sector; and

• change management and organization in the Reform Management Sector.

The existing Digitalization Sector will be reorganized within the new Directorate for Digital Transformation.

For the implementation of the reform program – Priority 1 - Consolidated Electronic Tax Administration, working groups have been formed and started working to prepare tender documentation with technical specifications for public procurement for the purposes of the following projects for the implementation of the new DIS:

• Establishment of a single register of taxpayers

• Electronic tax services and electronic mailbox

• Processing of tax returns and documents and tax assessment

• Debt and payment management and tax accounting

• Case management (tax procedure)

• Organizational and human resources management

Within Priority 2: Platform for Analytical Capacity of the PRO, activities related to the e-Invoice project were carried out, as follows:

• Finalization of the technical specification for the e-Invoice project.

• Technical dialogue held, which challenged changes in the tender documentation.

• Public procurement of the e-Invoice system has begun.

Within Priority 3: Security, stability and sustainability of DIS, a scan of the vulnerabilities/weaknesses of the PRO IT system/s (IT infrastructure, software, etc.) was performed, with the aim of taking measures to increase the security, confidentiality, integrity and access to information that will ensure the smooth functioning and security of data on taxpayers, tax and other public revenues.

In parallel with all activities, and for the successful implementation of the priorities of the Reform Program, a working group has been formed to work on the consolidation of existing data (paper and electronic) in the PRO for the needs of DIS, as a prerequisite for ensuring easier and smooth migration of data from one system to another and transition to using new functionalities and business processes in the PRO.

# Priority 3: Customs

Measure 2: Modernization of customs services and their digitalization

By implementing the measure for the modernization of customs services and their further digitalization, and by following the recommendations for harmonization and connection with the EU, the system of public finances, fiscal discipline and efficiency in the management and use of public resources will be strengthened, but transparency will also be promoted and efficient services and economic development will be ensured. This goal contributes to the provisions of the Program for the Reform of the Fiscal Fund, which supports the dialogue with the EU and helps in more efficient use of EU funds through the institutions of North Macedonia, on the way to accession to the EU.

Within the framework of this measure is planned “Implementation of modern systems in the direction of compliance with the Multi-Annual Strategic Plan of the EU (MASP), integration with European systems and procurement of appropriate hardware." Namely, the Customs Administration strives to be “SMART” which is in accordance with the policy of the World Customs Organization, which means: secure borders, automation, traceability and measurability, improvement of risk management and above all monitoring and application of the latest technology.

In the context of the implementation of the measure and the planned activities in the reporting period, activities are currently being carried out through which modern standards and practices are applied in the definition and realization of the business requirements of CARNM, using an appropriate project methodology for the implementation of new concepts and IT solutions, proven in the IT market. Also, continuous work is being done to improve the flow of information between all stakeholders in the activities related to the Customs Administration. Functionalities for data exchange data exchange from CDEPS with other with other institutions – takes place through the Interoperability Platform of the MISA. In 2024, in support of the projects for the implementation of NCTS Phase 5, the following trainings were held:

- Customs tariff training for customs officials working on the transit procedure,

- all 33 trainings on transit procedure procedures through NCTS 5, attended by 396 customs officers

- Three trainings and one information session were held for economic operators using the Customs Administration Portal for submitting transit customs declarations, attended by 85 representatives of economic operators.

In the reporting period, activities for the development of the external and governmental domain and increasing transparency and timely information of all participants in customs procedures, as well as users of IT systems, are also continuously implemented, through increased use of the Internet, intranet and modern social networks.

The Customs Administration is also working on the introduction of a complete paperless environment in the customs procedure, through the implementation of electronic systems from the e-Customs program, i.e. the Multi-Annual Strategic Plan of the EU (MASP), which are compatible with the systems and procedures in the European Union.

The connection of the customs administration to the appropriate IT infrastructure (CCN/CSI as well as to i.e. CA & CTA CONF), i.e. systems necessary for the testing of the new system, has been established.  The installation of the new NCTS 5 system has been completed, the necessary tests for the commissioning   were completed and it is expected it will be operational at the beginning of January 2025.

Training on the use of NCTS 5 are conducted for both customs staff and economic operators. The transition period at EU level will end in January 2025.

- Upgrade of the Integrated Tariff Environment (ITE) system

During 2024, the maintenance and development of the Integrated Tariff Environment (a system obtained with funds from IPA1) has been ensured for a period of 36 months. The new contract envisages the development of new or changes and upgrades to the existing interfaces for communication (web services) with EXIM, CDEPS, NCTS 4 and NCTS 5, modification of the BTI (Binding Tarrif Information) module for the purpose of electronic submission of the Request for Issuance of BTI according to the technical requirements of the EU and other adaptive changes. It is also envisaged to develop an interface between ITE and NCTS, for the needs of integration with NCTS 5, which should enable communication and exchange of data on tariff changes.

The security of the system is monitored on monthly basis, with submission of a report on the run checks and the activities taken with proposed instructions for improvement.

The Agreement for participation in the EU Customs Programme - CUSTOMS, which will cover the period 2021 – 2027 was signed by the European Commission and the Republic of North Macedonia, and it is ratified in June 2023 by the Assembly of the Republic of North Macedonia (Official Gazette No. 129/23 of 21.6.2023). Grant Agreement for the period 2021-2024 (October 2023) was also signed, under which the Programme officially becomes active. The European Commission authorized the Customs Administration to take an active part in the activities from the beginning of the programme and to use its benefits.  In the period January - December 2024, a total of 83 customs officers (64 online and 19 in person) participated in 27 events organized within the Customs Programme. The Customs Administration representatives had the opportunity to learn about the status of the activities implemented in the European Union by following the meetings of the following working groups: the European Customs Laboratories Network, e-Customs, the e-commerce subgroup within the Performance Group, the Expert Group on Prohibitions and Restrictions, the Network of National Transit Coordinators, the Network of National Coordinators of the Customs Programme, the Training Group and the Working Visits Group within the Customs Programme. Two working visits were organized.

Activities were also carried out for regular maintenance of the existing systems and hardware infrastructure for the operation of the ICT systems of the Customs Administration took place. Also, consideration of the needs and possibilities for further improvement of the services of the Customs Administration to the users is underway. The Customs Declaration and Excise Document Processing System – CDEPS is being regularly harmonized in the area related to excise duties and control functions with electronic excise documents, as per the daily operations.

The National Single Window System (NSW), currently under development and implementation, will ensure harmonization of processes and data for processing of permits/licenses used in cross-border movement of goods, by applying the regulations and technical specifications according to EU standards and practices.

By developing appropriate interfaces, the NSW is expected to integrate the national IT systems used in the Customs Administration and other government agencies, which include business processes from cross-border movement of goods.

All this is aimed at ensuring efficient communication between institutions and the business community in relation to cross-border trade. The project is financed with a loan from the World Bank.

Over the past few months, the National Single Window Implementation Working Group, established at national level, together with the team of consultants worked intensively on the preparation of technical specification as part of the tender documentation for the procurement of hardware and services for development of a software solution. The procurement notice for this system was published in May 2024. In accordance with the conclusions of the World Bank mission on the progress of the Project (held in early September 2024), the tender procedure for the design, procurement and installation of a National Single Window System was terminated, following concerns expressed by the Customs Administration, at the initiative of the Ministry of Transport.

The reason for the termination is the need to re-review the technical specification for the procurement in question, the critical implementation timeframe, as well as the insufficient engagement by the competent institutions. Hence, the Customs Administration has initiated activities to specify and revise the latest version of the technical specification for the system, with the aim of re-publishing the notice.

On 07.02.2024, an event was held to promote the NSW, at which the new system, the functionalities and the benefits that it will bring to both the private sector and state institutions in terms of simplifying work processes and accelerating cross-border trade were presented.

For legal, regulatory and procedural changes, a draft version of the draft Law on the Establishment of the NSW was prepared in June 2024. In the coming period, it will be presented to the Steering Committee, after which a procedure for adopting this law will be initiated, in order for it to be adopted before the system is put into production.

To modernize the ICT infrastructure Development and implementation of Data Warehouse is planned. Its implementation aims to provide centralized database of unified and high-quality data as grounds for quality decision-making process and, ultimately, improvement of business processes in the Customs Administration for better protection of the domestic market.

This project (its implementation programme/activities finalized) is financed with a grant from the Government of the Republic of Korea, for which a Memorandum of Cooperation was signed in October2023.

Under the IPA 2 Project “Supply of hardware and software for the Customs Administration and the State Audit Office” for procurement of ICT equipment and system software for upgrade of ICT infrastructure of the primary location data center and equipment has been installed and configured at a remote location ("Disaster Recovery" – DR). Equipment for DR site has been delivered, installed, tested and found compliant in accordance to the supply contract’s technical specification. The ICT system has been prepared for migration of the new hardware and software. After migration and data replication test scenarios are completed, the equipment for DR site was ready and is transferred and installed.  Therefore, the migration, upgrade of the database and replication of other ICT systems at a remote DR location is ongoing and the equipment is operational. Customs Administration has provided a Contract for maintenance of the equipment. In 2024, ongoing activities continued aiming at ensuring business continuity in the event of disaster recovery, which will allow all critical ICT systems to be activated at the Disaster Recovery Data Center location. This would contribute to implement the necessary requirements and standards for data protection and to ensure adequate protection of systems from disasters.

# Pillar III - Planning and Budget

# Priority 1: Budget Planning

Measure 1: Improving Medium-Term Planning

The key components of the medium-term fiscal policy involve a restructured budget policy and fiscal consolidation, designed to foster macroeconomic stability, accelerate economic growth, and enhance the domestic economy’s growth potential. Along with the focus on fiscal consolidation and budgetary savings, economic support is sustained through investments in infrastructure projects, restructuring public finances by increasing the share of capital expenditures, and strengthening transparency and accountability.

Fiscal consolidation continues by supporting the economy with investments in infrastructure projects, redesigning the structure of public finances through an increased share of capital expenditures, as well as strengthening the process of planning, execution and reporting of public finances. The participation of capital expenditures with an average participation of about 5% in GDP on an annual level, through which economic growth and development would be generated, is of essential importance.

The fiscal policy for the period 2025-2029 will be focused on improving macroeconomic stability and supporting economic activity through gradual fiscal consolidation, enhancing public finance management, and maintaining a high level of capital expenditures. At the same time, the budget deficit was reduced as a percentage of GDP from: 4.0% in 2025, 3.5% in 2026, 3% % in 2027, 3% in 2028 and 2,8% in 2029.

The key activities contributing to the improvement of medium-term planning, as outlined in the Fiscal Policy for the period 2025-2029, include:

- Improving macroeconomic stability, supporting economic activity, and accelerating   economic growth,

- Achieving fiscal rules through gradual fiscal consolidation and disciplined budgetary expenditure,

- Achieving a high level of capital expenditures by implementing investments in infrastructure projects,

- Reducing the informal economy and increasing revenue collection for the state budget,

- Strengthening the potential for growth of the domestic economy.

Measure 2: Improved Budget Planning and Developing Measurable Performance Indicators

The framework for implementing a sustainable fiscal policy, increasing budgetary discipline and responsibility, has been established with the new Budget Law, adopted by the Parliament in September 2022.

The 2024 budget was consistent with the Fiscal Sustainability and Economic Growth Plan, which is based on:

- Fiscal consolidation – through the establishment of measures for rationalization across different categories of expenditures, activities, and measures aimed at improving the efficiency and effectiveness of the public revenue collection system.

- Consistency of policies in the budget planning process – by fully linking budget planning with the Government Program, sectoral strategies, and alignment with the Economic Reform Program.

- Development of multi-year indicators to measure performance in the implementation of policies within the budget – to assess the effects of budgetary expenditures in relation to outcomes in the provision of public goods and services by budget beneficiaries.

In line with strengthening the budget preparation, execution, and reporting process according to the new Budget Law, missions with the U.S. Department of the Treasury were continuously carried out. A particularly significant development was the creation of new classifications according to the provisions of the new Budget Law. In December 2024, bylaws for the five classifications – administrative/organizational, economic, programmatic, functional, and classification of funding sources – were adopted. Their operationalization, as stipulated in Article 25 of the amendments to the Budget Law (“Official Gazette of the Republic of North Macedonia” No. 272/24), will begin on January 1, 2026.

Additionally, in April 2024, a mission titled “Spending Review in North Macedonia – Rules and Outline of Spending Review Manual” was organized with the International Monetary Fund. This mission is especially significant for understanding the analysis of budgetary costs, which is one of the key objectives and pillars of the fiscal consolidation process.

Measure 3: Fiscal consolidation for graduale and sustainable reduction of Budget Deficit

Fiscal consolidation continues through supporting the economy with investments in infrastructure projects, redesigning the structure of public finances by increasing the share of capital expenditures, as well as strengthening the process of planning, execution, and reporting on public finances.

# Priority 2: Strengthened Public Investment Management

Measure 1: Planning Sustainable Levels of Investment

Currently, the PIM department numbers 6 employees, out of 14 planned. In 2024, the PIM Department prepared the new Decree on managing public investment projects, as a by- law stemming from the new OBL (article 20), in order to establish a structured and comprehensive approach to decision making for the proposed public investment projects. The PIM decree regulates the manner of defining, preparing reviewing, evaluating and prioritizing new public investment projects, monitoring and reporting on the implementation and ex-post review of public investment projects as well as the roles and responsibilities of the entities involved in each of the stages of the PIM process. The Public Investment Management Decree is in the governmental procedure for adoption and will start to apply after its adoption.

Measure 2: Improved project appraisal, selection and allocation of resources for capital investments

Draft Decree on Public Investment Management prescribes a methodology/guidelines for project evaluation. It was adopted by the Government in July 2024, conditional on amending the OBL. It is expected that the Decree would be published in the Official Gazette by the end of 2024 and shall start to apply in January 2025. In addition, feasibility study guidelines have been developed which provide detailed recommendations for preparation of feasibility studies. These guidelines will be published by the Ministry of finance after the adoption of the PIM Decree.

The first training of officials from relevant public institutions on the basics of public investment management was conducted in May 2024, with technical assistance from the World Bank.

Measure 3: Efficient and effective monitoring of capital investments

Specific procedures for monitoring of implementation of public investment projects are set by the Government with the new PIM Decree.

The PIM module to be developed under the IFMIS is expected to support the PIM functions related to monitoring.

In order to bridge the period until the new IFMIS PIM module becomes operational, the MoF started to develop a short - term IT solution for public investment management (PIMIS) to collect and store basic information on public investment projects.

Two missions were carried out in the MoF (in June and October 2024) for adaptation of the Excel-based PIMIS developed by IMF-FAD to the MoF needs, so that it can be used as transitory IT solution that will provide the MoF with a database of projects from which to select budget candidates and monitor implementation of projects.

# Priority 3: Effective Instruments under the Growth Acceleration Plan

Measure 1: Establishment of Different Funds in the State Institutions and Development of Different Financial Instruments

This measure envisages establishment of 6 different Funds the objective of which, under this Priority, is to provide easier access to financial resources for companies, financing investments in the field of energy efficiency, supporting export-oriented companies, encouraging innovative activities. So far, two out of six of the envisaged Funds have been established under this measure: Guarantee Fund and Research and Development Fund, established and operating within the Development Bank of the Republic of North Macedonia. The proposed law for amendment and supplementation on the Law on the Development Bank of North Macedonia was adopted by the Government on July 25, 2023 Then it was adopted by the Parliament on October 3, 2023. With that the legal framework for the Energy Efficiency Fund was created and the possibility of its implementation. Regarding the Fund that should be established within the Directorate for Technological Industrial Development Zones, amendments from the Law on Technological Industrial Development Zones that will enable the Directorate for Technological Industrial Development Zones to establish and manage the fund are in government procedure. Other Funds envisaged under this measure are to be established in the coming period.

Measure 2: Strengthening the Capacities of Various Institution

The ’s objective is to ensure effective implementation of the Growth Acceleration Plan, by establishing a management structure which will cover the entire project management process, including feedback to accelerate effectiveness over the years. It envisages 3 activities - establishment of a Delivery Unit for infrastructure project coordination, establishment of a Project Monitoring Unit and establishment of a Capacity Building and Training Unit. The establishment of a unit for coordination of infrastructure projects is in the Government procedure, while the establishment of a unit for monitoring projects and the establishment of a unit for capacity building and training as these units should be established during the next period.

# Pillar IV - Public Procurement

# Priority 1: Public Procurement Policy

Measure 1: Strengthening institutional capacities

Cooperation among the key institutions in the public procurement system within the Advisory Group continued in 2024. Two regular working meetings were held, during which various issues related to public procurement were discussed.

Additionally, the Coordinating Body continued its cooperation within the framework of monitoring the implementation of the Strategy for Developing the Public Procurement System 2022-2026, through which the implementation status of the measures and activities outlined in the Strategy by the competent institutions is monitored. The draft Annual Monitoring Report for implementation of the Strategy for 2023 and 2024 is in process of preparation, as well as the draft Action Plan for the implementation of the Strategy for 2025.

In terms of supporting contracting authorities and strengthening their capacities, the PPB continued to prepare and publish new methodological tools. PPB published three new brochures on its website, covering different aspects of the implementation of the Law on Public Procurement, as follows:

- Manual on Abnormally Low Tenders – The aim of this manual is to contribute to improving the evaluation skills, particularly regarding offers with an “abnormally low tenders”, through explanations and examples, in accordance with the national legal framework and international good practices.

- Manual on the Use of the Law on Public Procurement in Support of Economic Operators with a Strong Social Mission (Reserved Contracts) – This manual clarifies reserved contracts to encourage the strategic use of public procurement to achieve important social goals, such as social aspects in procurement and encouraging the participation of small or medium-sized enterprises.

- Recommendations for the Application of the Law on Public Procurement in an Extreme Urgency Situations – This brochure contains recommendations based on accepted good practices and guidelines, aimed at the efficient and accurate implementation of the LPP by the contracting authorities, related to public procurements in situations of extreme urgency.

Guided by the idea of exchanging opinions, knowledge, and experiences in the implementation of the Law on Public Procurement, the PPB organized "Open Doors" with contracting authorities and economic operators as direct practitioners of the LPP, in April and December 2024. These events aimed to identify weaknesses and plan appropriate activities for improved legal implementation in the future.

In order to establish a new education system for the Public Procurement Bureau, a comprehensive analysis of the existing education system was conducted. The partners from the Twinning project for "Strengthening the Functions of Budget Planning, Execution, and Internal Control," where the PPB was a beneficiary of Component 3, prepared an analysis and provided specific proposals regarding the Programme and the education system. The analysis also includes certain recommendations from the European Commission and SIGMA (Joint Initiative of the OECD and the European Union) related to the professionalization of public procurement officials. Taking this into account, the PPB has undertaken a review of the concept of certification and recertification and concluded that the Education Programme should be amended. The new education programmes should enable the continuous improvement of knowledge, skills, and good practices in the implementation of public procurement, thereby facilitating the professionalization of public procurement officials. At the same time, the analysis of the evaluation questionnaires from the conducted certification and recertification trainings identified weaknesses that need to be addressed, and the suggestions from candidates regarding the Programme have also been considered.

To redesign the existing Education Programme in line with the above, it is crucial to adopt the amendments to the LPP, covering the education.

Regarding the strengthening of capacities for identifying and preventing illegal actions and corruption in public procurement, the PPB organized two separate two-day workshops in 2024, in cooperation with the Department for Suppression of Organized and Serious Crime at the Ministry of Interior – Unit for Corruption, Financial Crime, and Financial Investigation.

Furthermore, in 2024, the Bureau, in cooperation with the World Bank, held a workshop on the benefits of implementing red flag indicators in public procurement. The Report on Established Indicators for Monitoring Risks in Public Procurement for 2023 has been published on the PPB's website.

# Priority 2: Public Private Partnerships (PPPs)

The goal of this priority is the introduction of new policies in the sphere of public private partnership in the Republic of North Macedonia and the provision of all prerequisites in the development of an effective system for public private partnership that will enable the activation of previously inactive funds for the construction of large buildings and public buildings interest, while stimulating competition and achieving the best value for money. The Draft Law on Public-Private Partnership and the Draft Law on Concessions of Goods of General Interest have been forwarded to the relevant institutions for an opinion thereon. The process of harmonizing these laws with the European Commission and the Secretariat for Legislation was prolonged and lasted almost six months, especially considering the fact that elections were held in 2024.

On July 15, 2024, the Law on Concessions and Public Private Partnership (“Official Gazette of the Republic of North Macedonia” no.147/24) was adopted, whereby the competence in the area of concessions and public private partnership was transferred to the competence of the new Ministry of Energy, Mining and Mineral Resources.

# Priority 3: Appeal Mechanism

Measure 1: Strengthening the legal and regulatory framework of legal protection in the public procurement process

#### The activity of drafting of a special law for legal protection in the field of public procurement implies complete improvement of the system for legal protection in public procurement by developing new tools for acquiring theoretical and practical knowledge, professional skills and competencies for professional, economical, efficient and effective implementation of public procurement procedures at all levels.  Currently, comparative analyzes are being made and the experiences of the EU member states are being observed so that the preparation of the special law for legal protection in the field of public procurement can begin.

Measure 2: Strengthening the administrative capacity of the SAC

In order to strengthen the capacities of the SAC to achieve the necessary level of efficiency of the SAC and for the proper functioning of the public procurement system as a whole, it is necessary to increase the number of civil servants in the professional service of the SAC which would increase the transparency, efficiency and the effectiveness of the SAC. In the reporting period January-December 2024, no new employment was realized in the SAC.

During 2024, the State Commission for Public Procurement has no real reform activities for the management of public finances.

# Pillar V - Integrated Public Finances

# Priority 1. Implementation of an Integrated Financial Management Information System (IFMIS) to Support the Implementation of PFM Reforms and Organic Budget Law

Measure 1: IFMIS is fully operational to support the implementation of OBL reforms

This measure includes three activities: (1) Development of IFMIS as an integrated, centralized, web-based system that supports decentralized operations; (2) Expansion of the Ministry of Finance's (MoF) ICT infrastructure, in line with the “whole-of-government” approach, into which IFMIS will be integrated; and (3) Capacity building, including the Budget Law Reform Working Group, training, and change management to support the Budget Law reforms and the functioning of IFMIS at the national level.

The basis for implementing this measure, i.e., the priority, stems from the Law on Budgets, adopted in September 2022, with deferred application starting January 1, 2026. This law regulates public finance management reforms. One of the key reforms envisaged by this law is the establishment and implementation of an Integrated Public Finance Management Information System (IFMIS) to support the implementation of reforms outlined in the law. These reforms include, among other things, the establishment of a multi-annual budget framework, the introduction of a public investment management function, improving budget execution through an automated system for monitoring obligations (including multi-annual obligations and centralized data on undertaken obligations), management of the state's basic financial and non-financial assets, and improved debt management.

The IFMIS Development and Implementation Project, along with the Integrated Tax Information System Development and Implementation Project and the State Aid Management Information System Development and Implementation Project, is supported by a World Bank loan of EUR 20 million and a grant of EUR 5 million from the European Commission. The World Bank loan and European Commission grant agreements were signed in January 2023.

Part of the funds from the World Bank loan are allocated for establishing a Project Unit (PU) for the implementation of the "Project for Building Effective, Transparent, and Accountable Public Finance Management Institutions," which includes the development and implementation of the IFMIS system. The staffing of this unit was completed in May 2023, with the appointment of a PU Project Manager, a Financial Management Specialist, and a Procurement Specialist.

In accordance with Article 107 of the Budget Law, the Minister of Finance established a Working Body (WB) in May 2023. The WB is responsible for the implementation, upgrading, optimization, execution, regulation, maintenance, control, staff education, and analysis of all processes and functionalities of the IFMIS system.

During 2023, the WB adopted the terms of reference for engaging a consultancy firm to provide advisory and technical assistance in developing and implementing IFMIS and managing changes related to IFMIS. These terms of reference were approved by the World Bank, after which a call for expressions of interest by economic operators was published in July 2023.

The WB also supplemented the functional and technical specifications for IFMIS with a new module for public internal financial control and fiscal risk reports. These specifications were formally adopted, along with the tender documentation for the procurement of IFMIS. The World Bank approved both the tender documentation and the functional and technical specifications, after which a public tender call for the procurement of IFMIS was published in November 2023. Additionally, a call for expressions of interest was published in February 2024 for technical assistance in operationalizing change management to improve communication and stakeholder involvement.

# Priority 2: Strengthen the Accounting of Budgets and Budget Users

Measure 1: Strengthening the Accounting System by Applying New Accounting Practices

In 2023, by the consultants engaged through the UNDP project were held two missions regarding the preparation of the Strategy for Improvement of Budget Institutions’ Accounting. In June 2023 were presented the GAP Analysis for the introduction of accrual accounting in the Republic of North Macedonia the prepared Strategy with the Action Plan. Following the adoption of the Strategy, new regulatory framework will be prepared for implementing reforms in the field of budget accounting in order to adoption of new accounting practices and standards for financial reporting in the public sector.

# Priority 3: Public Finance Academy

Measure 1: Establishing a Public Finance Academy

The Public Finance Academy was established by the Rulebook on Organizational Setup and the Ministry of Finance No. 01-11277/1 of December 29, 2022.

The Public Finance Academy comprises a team of nine employees who, throughout 2024, actively participated in trainings, workshops, study visits, and conferences. Through these activities, the employees significantly improved their professional skills and competencies, further strengthening the Academy's capacity to fulfill its mission.

A training room has been equipped and adapted within the Ministry of Finance, which provides modern conditions for organizing educational activities and supports the creation of an environment for learning and professional development.

Measure 2: Development and Implementation of a Curriculum

At the beginning of 2024, the Minister of Finance adopted the Annual Training Program for Administrative servants for 2024, in which six trainings in the field of public finance were planned. Of the planned, four one-day trainings were successfully implemented. Additionally, in cooperation with the American Chamber of Commerce, an ad hoc training on the topic "The Role of the Public Sector in Supporting ESG (Environmental, Social and Governance) Standards and Sustainable Development Regulations" was conducted for a duration of five working days.

The Academy of Public Finance undertook activities to implement the Training Needs Analysis for 2025 for public sector, which will serve as the basis for the preparation of the Annual Training Program for public sector employees for 2025.

Through the IPA Twinning Project "Strengthening the Functions of Budget Planning, Execution and Internal Control", a Curriculum Manual was developed as a basic document for structuring the trainings. Within the same project, two trainings for trainers were conducted – one at the basic and one at the advanced level. As a result of these activities, a total of 39 trainers were certified and included in the trainer register.

Additionally, in cooperation with CEF Ljubljana, was developed a concept for the transformation of the Academy into a Learning Organisation.

Measure 3: Inter-institutional cooperation

The Academy maintains ongoing collaboration with the National Academy of Finance and Economics of the Netherlands and CEF Ljubljana. As a result of the bilateral cooperation between the Ministry of Finance of the Republic of North Macedonia and the Ministry of Finance of the Netherlands, experts from the National Academy of Finance and Economics with joint collaboration with the Academy, in December 2024 prepared a proposal for an annual work program of the Academy, which includes clearly defined indicators for measuring efficiency and performance results.

Furthermore, initiatives were taken to conclude memorandums of understanding with domestic and foreign institutions/organizations. On December 17, 2024, a memorandum of understanding was officially signed with the American Chamber of Commerce, which opened up new opportunities for partnerships and development.

The Academy undertook activities to establish a network of contacts with institutions at the central level, in order to promote cooperation in organizing trainings, and also established cooperation with the Tax Academy at the Public Revenue Office.

# Pillar VI - Public Internal Financial Control

# Priority 1. Financial Management and Internal Control

Measure 1: Establishment of a Comprehensive System of Financial Management Controls based on Risk Management

The Ministry of Finance, through the Central Harmonization Unit, updated the text of the draft Law on the Internal Financial Control System in the Public Sector. The need to update the text arose in accordance with the Rules of Procedure of the RNM Assembly, and also due to the publication of new international standards for internal audit. At the same time, the text of the draft law is fully aligned with the new Law on Budgets, and other technical corrections have been made. After the completion of the entire legislative procedure by all institutions, i.e. after the adoption of the law by the RSM Assembly, the Law on the Internal Financial Control System in the Public Sector was published on December 17, 2024 in the Official Gazette of the RSM No. 255.

In 2024, within the framework of the twinning project "Strengthening the functions of budget planning, execution and internal control", the draft versions of the Financial Management and Control Manual and the Guidelines on the manner of conducting a review of the quality of financial management and control were revised. These documents, after they are finally harmonized with the Law on the Internal Financial Control System in the Public Sector, will be officially published.

In order to strengthen the capacities of the Central Harmonization Unit (CHU) to review the quality of financial management and control, with the support of experts from the twinning project, three pilot checks of the quality of financial management and control were conducted. Two new people have been employed in the Central Harmonization Unit, an Assistant Head of CHU and a Junior associate. The staffing of CHU should continue in 2025.

At the 38th session of the Government of the Republic of Macedonia held on 10.12.202, the "Annual Report on the Functioning of the Public Internal Financial Control System for 2023" was adopted with appropriate conclusions for the improvement of financial management and control.

The Central Harmonization Unit, independently and in cooperation with foreign experts, organized/conducted 9 trainings/workshops for employees in the financial affairs units and for employees of the CHU.

# Priority 2. Internal Audit

Measure 1: Strengthening the Quality of Work of the Internal Audit Units in the Ministries

With the Law on the system of internal financial control in the public sector, new criteria have been established for public entities regarding the obligation to establish and the manner of staffing the internal audit units.

In order to strengthen the capacities of the Central Harmonization Unit (CHU) to review the quality of financial management and control, with the support of experts from the twinning project, three pilot quality checks of the operation of internal audit units were conducted. The Central Harmonization Unit has employed two new people, an Assistant Head of CHU and a junior associate. The staffing of CHU should continue in 2024.

At the 38th session of the Government of the Republic of Macedonia held on 10.12.202, the "Annual Report on the Functioning of the Public Internal Financial Control System for 2023" was adopted with appropriate conclusions for the improvement of internal audit.

The Central Harmonization Unit, independently and in cooperation with foreign experts, organized/conducted 13 trainings/workshops for employees in the internal audit units and for employees of the CEH.

# Priority 3. Financial Inspection

Measure 1: Strengthening the Institutional Basis of the Financial Inspection Function

After entering into force of the new Law on Financial Inspection in the Public Sector (*) (“Official Gazette of Republic of North Macedonia” no.19/23), on 7th of February 2023, within the reporting period ending with 31th of December 2024, the procedure for the preparation and adoption of 14 by-laws and internal acts is finalised and three by-laws and internal acts are in the final stage of preparation. Namely, the Guidelines for the manner of monitoring, measuring, and evaluating the effectiveness of inspectors, as a basis for awarding prize for the best inspector in accordance with the legally established criteria is in final phase of preparation. The Procedure for conducting financial inspections with annexes to it, is prepared and sent to the team for quality for consideration.

Measure 2: Strengthening the Capacity of Financial Inspection Human Resources

Within the IPA Twinning project "Strengthening the budget planning, execution and internal control functions", the Program for theoretical training and practical work for obtaining a license for a financial inspector, as well as the form and content of the certificate for successfully completed training has been prepared, but its not yet aproved. The Program for taking an exam for obtaining a license for a financial inspector and the Training Program for performing financial inspection are adopted and published in the Official Gazzete of Republic of North Macedonia in the course of 2024.

# Pillar VII - External Control and Parliamentary Oversight

# Priority 1. External Audit

Measure 1: Strengthen the legal framework for external audit

Within the Twinning project "Improvement of external audit and parliamentary oversight", an assessment of the state audit legal framework was performed and recommendations were made for strengthening external audit legal framework and achieving SAO constitutional independence as well as for strengthening financial and operational independence in line with international standards and EU best practice.

As a result of these activities, with support of the Twinning project, SAO prepared:

- Proposals for draft amendments to the Constitution of the Republic of North Macedonia for regulating SAO as a constitutional category;

- Draft new State Audit Law for strengthening SAO financial and operational independence.

Proposals of draft amendments to the Constitution of the Republic of North Macedonia, prepared by the State Audit Office were submitted to the Ministry of Justice as a competent ministry, to the Parliament and the Government. The SAO has been informed by the competent authorities that this initiative aims to strengthen SAO independence and that it will be taken into account, but having in mind these proposals are only suggestions and that manner require special treatment in our legislation and involvement of all stakeholders in the process for which SAO will be further notified. In this direction SAO expects that the competent ministry, in coordination with all stakeholders in the process, to submit an initiative to the Assembly of the Republic of North Macedonia for the regulating State Audit Office in the Constitution of the Republic of North Macedonia and to strengthen SAO independence.

The new draft State Audit Law envisages strengthening financial and operational independence of the State Audit Office and acting upon audit recommendations by the audited entities and creates opportunities for review of final audit reports by the Parliament. These are significant improvements to the state audit legislation in line with EU requirements and the International Standards of Supreme Audit Institutions (ISSAIs). Opinion on the draft law was provided from: the twinning partner SAIs of the Republic of Croatia and the Republic of Bulgaria DG Budget of the European Commission and INTOSAI Development Initiative (IDI) as well as the Peer Reviewer SAI of Poland.

In February 2023, Ministry of Finance started the process of public consultation for the State Audit Law on the platform National Electronic Registry of Regulations (www.ener.gov.mk). Ministry of Finance submitted the draft State Audit Law to the Secretary for legislation, Ministry of Information Society and Administration and Ministry for Justice opinions were requested.

During the reporting period, the Auditor General held meetings with the Minister of Justice and the Minister of Administration and Information Society regarding the State Audit Law and in June 2023 an opinion was provided by the Secretariat for Legislation.

Upon this opinion SAO prepared a new draft SAL which was submitted to MF. During this period AG held meetings with Minister of Justice and Minister of Information Society and Administration concerning SAL.

.

The Auditor General handed over the draft State Audit Law to the new Minister of Finance for further action at the end of September 2024. This new law aligns with the relevant legal framework.

It is important to highlight that on 19 July 2024, the State Audit Office and the Supreme Audit Office of the Republic of Poland (NIK) signed a Memorandum of Understanding for the implementation of a Peer Review of the SAO operation[1]. The goal of this Peer Review is to assess SAO compliance with INTOSAI international auditing standards (ISSAIs) and provide support and recommendations for improvements in the following areas:

- Independence,

- Human resource management,

- Implementation of methodologies for financial audit, compliance audit, and performance audit, including reporting on audit findings, and

- Communication and activities with stakeholders, as well as adding value in terms of transparency, accountability, and improving citizens' lives.

The Peer Review report highlighted that the SAO strategic documents are developed following international standards and best practices. The applied audit methodologies for financial, compliance, and performance audits align with ISSAIs. The port commended SAO's modern approach to communication, including the well-prepared communication strategy, increasing media presence (including social media), and impressive national and international engagement. SAO operations comply with international standards and best practices for supreme audit institutions, with the exception of full constitutional independence. The final report from the conducted Peer Review is expected to be delivered to SAO in due course.

On December 27, 2024, the Ministry of Public Administration introduced new versions of the Law on Public Administration and the Law on Employees in the Public Sector for public consultation on the ENER platform. Additionally adopted bylaw Rulebook for organizational classification from the new Budget Law, does not envisage SAO as a separate parent Budget user.

The proposed legal framework and bylaws raise concerns about the operational and financial independence of the SAO, as well as the status of its employees. These provisions do not align with the State Audit Law and ISSAIs .

Initiating procedure for adoption of the new State Audit Law as well as for adoption of constitutional amendments is expected in the upcoming period.

Measure 2: Strengthening the institutional capacities and HR capacities of the SAO

Activity 1: Preparing new or improved SAO strategic, planning and methodology acts

The annual implementation of SAO Development Strategy 2023-2027 was carried out through the activities contained in SAO Annual Work Program for 2024, which envisages 89 audits in total, out of which 73 regularity audits, 13 performance audits, 2 compliance audit, and 1 real-time audit. SAO Development Strategy is closely related to the priorities and measures in PFM Reform Program 2022 -2025.

In 2024, SAO is implementing the strategic documents for HR Management 2024-2027, Strategic Audit Plan 2024-2027, Risk Management 2024-2027, and Communication Strategy 2024-2027. Additionally, SAO IT Strategy 2023 – 2027 was updated in June 2024, based on the input provided with the participation of SAO representatives in the IDI LOTA pioneers’ program, which aims to integrate technology into the world of SAI auditing through the development of a strategy for leveraging technology in audits and auditing the use of technology by governments. These strategic documents align with the SAO Development Strategy 2023-2027.

In 2024, a new Regularity Audit (Financial and Compliance Audit) Manual was adopted to align with the relevant ISSAIs for financial and compliance audit.

A new Learning Management Platform as well as course on Performance audit was developed and a new course on SAO communication practices is beeing developed to strengthen SAO capacities.

The remaining methodology will be prepared in accordance with the planned activities in SAO strategic and planning documents.

Activity 2: Strengthening capacities for conducting audits

The State Audit Office continuously invests in strengthening the skills and knowledge of state auditors, which ensures additional quality in work and maintaining professional integrity as an institution-bearer of progress in the public funds management. SAO Annual Plan for Continuous Professional Development for 2024 was implemented with internal resources and by using national and international experts in the relevant filed as well as with international support and cooperation with other SAIs and other international organizations.

In 2024 with support of our partners and collaborators,  SAO completed the trainings part of SAO Annual plan for Continuous Professional Development focused on improvement of the knowledge of the state auditors in the field of accounting, new amendments to the legal regulation, use of IT resources, IT tools in the audit and information security, audit on LSG, financial audit, the lessons learned from the quality assurance and control of quality, as well as audit planning and risk analysis, value for money audit, developing soft skills and personal development.

Within the framework of the Performance Audit Training Program for the Western Balkans and Turkey, which is implemented by the Swedish National Audit Office (SNAO), several workshops on performance audit were carried out and SAO participated with 2 audit teams.

The Auditor General and Deputy Auditor General participated on the XII EUROSAI Congress, hosted by the SAI Israel as the new chairman of EUROSAI for the period 2024-2027.

During the reporting period, a delegation from the SAO, led by the Auditor General, held a bilateral meeting with the President of the Supreme Audit Institution of the Slovak Republic, with the support of UNDP. The discussions focused on the use of software applications in audits and the organization of joint events and training sessions of mutual interest, in accordance with the Memorandum of Cooperation between the two institutions.

In June 2024, in Montenegro, the SAO delegation led by the Auditor General attended the Academy for financing the Sustainable Development Goals (SDG), where the representatives from the UNDP and the Western Balkans countries, shared information and best practices on the SDG financing.

At the invitation of the State Audit Institution of Montenegro and WFD Western Balkans, SAO employees participated on a Workshop for development of internal procedures for the use of social networks as well as auditing the State Core budget.

Cooperation with the Office of the Auditor General (OAGN) was implemented in accordance with the signed Memorandum of Understanding and the Project Document. Within the framework of this cooperation, SAO is supported by the OAGN in performance audits, IT audits and IT support in audits and development of the Innovation Laboratory. In 2024, the SAO in partnership with the Office of the Auditor General of Norway (OAGN) hosted severals workshop on Basic audit of Active Directory Domain Services, Active Directory, MS SQL auditing, and QS08 training. IT auditors from the SAI of Kosovo were also invited to participate in this training. The primary objective of the training was to investigate the potential applications of Active Directory and MS SQL auditing programs in the context of information security auditing, thereby addressing the challenges posed by cyber threats. On November 19, 2024, a new web application for auditing public procurement was presented at the Supreme Audit Office (SAO). This development was the result of collaboration between the SAO and the Office of the Auditor General of Norway (OAGN) as part of an institutional cooperation project involving both Supreme Audit Institutions. The web application was inspired by an idea submitted during last year's Hackathon, which is part of the initiative to develop an Innovative Laboratory at the SAO. This initiative aims to create innovative solutions that enhance the audit process.

The capacity of State Auditors to conduct performance audits have been strengthened through the implementation of 2 pilot performance audits and 1 IT audit in collaboration with the SAI of Norway(OAGN), 1 value-for-money audit in cooperation with the UK NAO supported by the WFD, and 2 performance audits focused on public investment projects supported by the World Bank.

Representatives of the State Audit Office, participated in an advanced training, organized by the Joint Working Group on Audit Activities (JWGAA) of the European Union, under the guidance of the SAI of Sweden. The training focused on in-depth analysis of performance audits, i.e., how to recognize the need to analyze the real causes of problems, rather than limiting themselves to merely ascertaining their existence and detecting deviations from audit criteria.

Within the scope of the performance audit cooperation organized by the Supreme Audit Institution of Sweden, in the period 13-17 May 2024 SAO representatives participated on the last session of the training program on the performance audit that was held in Stockholm, Sweden.

SAO has joined the INTOSAI WGEA initiative called CLIMATE SCANNER, in this regard, SAO is conducting a performance audit on preparedness of the Republic of North Macedonia to deal with climate change, which will contribute to the environmental protection as a universal commitment.

Within the framework of the project to strengthen the capacities of the State Audit Office for conducting performance audits on public finance projects financed by the World Bank, together with colleagues from Ernest&Young from Türkiye, the Auditor General and SAO representatives participated in the traininga on performance audits of public investment projects and new Public Investment Management Performance Audit Guideline was developed. Additionally, SAO representatives attended a World Bank training in Vienna on public finance management for climate action and infrastructure improvement in Europe and Central Asia. The SAO shared its experience in performance audits of public investment projects and emphasized the importance of coordination with the Ministry of Finance.

In the period 27-29.02.2024, delegation of the SAO and the Ministry of Finance participate in a Conference of the Network of Supreme Audit Institutions of candidate countries and potential candidates for European Union membership, on "Auditing the final account of the state budget", in Budva, Montenegro. In a panel discussion on "Maximizing the efficiency and benefits of the audit of the state budget", the Auditor General presented and shared the experience of the State Audit Office in conducting the audit of the RNM budget, addressing the key established states and communication with the parties concerned. As part of the conference's activities, Auditor General and Senate President signed a Memorandum of Co-operation between the State Audit Office and the State Audit Institution of Montenegro

In 2024, SAO representative actively participated in the implementation of the Executive Program "Effective management and controls against fraud in the use of European Union funding instruments", organized by the Luiss University of Law in Rome, Republic of Italy.

From 16 to 20 September 2024, an SAO representative attended the workshop on "Leading Digital Change", held at the premises of the University of Toledo, Spain. The workshop is part of the International Development Initiative (IDI's) pICTure initiative, which is aligned with the IDI Strategic Plan 2029.

The successful co-operation between the State Audit Office (SAO) and the State Audit Institution (SAI) of Serbia, which has resulted from prior cooperative audits, continued through the implementation of a third cooperative performance audit entitled "Urban Planning of Green Infrastructure in Cities." During the current reporting period, representatives from both institutions delivered presentations detailing the findings from the execution phase of this audit.

SAO employees’ capacities were strengthened in the framework of the Swiss Scholarship Program as part of the Parliamentary Support Program. The program has financially supported the parliamentary staff in their professional development since 2018, and SAO employees have been included since 2023.

SAO representatives attended a three-day workshop on gender statistics with a focus on "Domestic Violence and the Road to Justice in the Republic of North Macedonia", organized by UN Women.

SAO representatives participated in several training events organized by CIPFA as part of the CPD of the ICCRM, including workshops on Corruption Risk Assessment, focusing on the drivers of corruption and control assessments, and culture, climate change and corruption.

In preparation for the implementation of the new IFRS standards in 2025, a workshop for Preparation of cash flow statement, IFRS 15-Revenue from Contracts with Customers and IFRS 16-Leases. Additionally, two SAO representatives successfully completed the IFRS Training of Trainers. These training courses aimed to strengthen the capacity of the SAO and the accountancy profession in the country resulting in enhanced quality of IFRS-based financial statements.

The SAO joined the IDI INTOSAI SAI Young Leader Program, with two SAO representatives selected—a SAI Young Leader and a SAI Young Leader Coach. This program aims to develop the SAO's change strategy, focusing on building stakeholder bridges for high-impact audits.

SAO representatives, as part of the IDI INTOSAI LOTA programme, participated in the LOTA Talks workshop organized by IDI INTOSAI. The workshop covered key topics, including continuous auditing of municipal procedures vulnerable to corruption, automation of financial audit data processing, the development of an analytics platform for continuous monitoring, and advanced data analytics for governance risk assessments. Additionally, an online meeting was held to discuss the ongoing compliance audit of the "System for Integrated Resource Planning – ERP System" included in the 2024 SAO Annual Work Program.

Delegation led by Auditor General Acevski participated in the Conference on National Evaluation Capacities (NEC 2024), organized by the UNDP Independent Evaluation Office (IEO), the China International Development Cooperation Agency (CIDCA), and the Global Evaluation Initiative (GEI) in Beijing, People's Republic of China. The objective of the conference is to enhance the capacities of governments, modernize their systems, and promote collaboration across inter-sectoral policies. The focus is on effectively and efficiently addressing significant challenges, including the pandemic, the food crisis, and the energy crisis.

On December 16, 2024, the Auditor General, held a working meeting with representatives from the World Bank, led by the World Bank Country Manager. During the meeting, the World Bank representatives acknowledged the critical role that the State Audit Office plays in the public sector. They reaffirmed their commitment to continue supporting SAO activities, especially in auditing the system for monitoring capital investments in the country financed by the World Bank. An official agreement is expected to be signed between the two parties in the near future. This document will define the specific rights and obligations of each party, aimed at strengthening their cooperation and ensuring the achievement of the desired outcomes.

Within the framework of the project activities which Within the framework of the project activities which is implemented by IFES, 7 state auditors continued the data science academy with the course “Programming in Python for Data Science” in order to improve their analytical skills, which are key skills for data analysis that enable them to more easily deal with business problems by forming decisions in efficient way. Additionally, 3 SAO employees completed Graphic Design Academy, to strengthen their graphic design skills, aiming to visually improve presentation of audit reports in a friendly way.

Additionally, SAO employees continuously attend workshops organized by Agency for the Protection of the Right to Free Access to Public Information, SCPC and the Ministry of Finance - Public Finance Academy Department.

SAO Management and employees during the reporting period attended to a number of conferences and training events organized by CEF Slovenia, focused on strengthening the accounting and audit capacities through cooperation of the regional expert network, improving public finance management etc.

The Annual Work Program for 2023 was successfully implemented completely and included: 66 audits, of which 48 regularity audits (financial audit and compliance audit), 11 performance audits, 3 compliance audits and 4 follow up audits. All final audit reports have been submitted to the Assembly of RNM and published on SAO website. The Annual Report on performed audits and SAO operation for 2023 has been prepared and will be submitted to the Assembly within the legally prescribed deadline by the end of June 2024, and published on SAO website in three languages - Macedonian, Albanian and English  (https://dzr.mk/sites/default/files/dzr/doc/izvestai/Godisen_izvestaj_MKD_2023.pdf ).

With the audits conducted in 2023, the scope of audited expenditure of the Budget of the Republic of North Macedonia for 2022 is 84%, which is 2% more than the previous year. Regarding the audited public expenditure, we note an increase of 111.122 million denars, i.e., 39% more than the Annual Work Program for 2022.

Additionally, the added value of performed audits was enhanced, particularly in terms of identified less calculated, less returned, or less paid funds to the Budget of the Republic of North Macedonia and to municipal budgets, indicating the significant contribution of SAO towards strengthening institutions and managerial accountability. The Annual Report on performed audits and operation of the State Audit Office for 2023 was reviewed and adopted at the Fourteenth Session of the Assembly of the Republic of North Macedonia on 12 September 2024. The Assembly reviewed and adopted conclusions on the Annual Report. The conclusions are in support of SAO activities, implementation of recommendations, overcoming systemic weaknesses and ambiguities identified in laws and by laws, and strengthening the cooperation with the Assembly. Earlier, on 6 September 2024, Mr. Acevski presented the Annual Report for 2023 at the third session of the Finance and Budget Committee.

From 2-4 September 2024, SAO employees participated in a workshop titled "Preparing the SAO Annual Work Program based on the National Development Strategy and Financial Statement Analysis," supported by the United Nations Development Program (UNDP) in North Macedonia. The workshop focused on aligning the SAO Annual Work Program with the National Development Strategy, aiming to promote a more developed economy and improve citizen well-being. It covered topics such as strategic priorities, key indicators of the National Development Strategy, and their integration into the SAO Annual Work Program. Additionally, the workshop addressed the application of cost-benefit analysis in auditing investment projects, evaluating the efficiency of public sector investments, analyzing financial statements, and ensuring internal strategic documents are aligned with national development goals.

In December 2024, SAO adopted the Annual Work Program of the State Audit Office for 2025. Тhe Annual Program for 2025, contains 89 audits, out of which 73 regularity audits, 13 performance audits, 2 compliance audit, and 1 real-time audit. In defining performance audits for this Annual Program, we applied the following criteria: SAO strategic objectives, UN SDGs, National Delepoment Strategy 2024-2044, and criteria set by the assessment methodology of OECD-SIGMA. Applying the principles of transparency and openness in the preparation of the Annual Work Program, SAO enabled and placed on the website a "tab" form for requesting an audit as well as e-mail was sent to all 1.215 interested parties and posted on SAO Facebook page. For the second consecutive year, with support of WFD, the State Audit Office (SAO), hosted the workshop titled “Inclusion of Civil Society Organizations and the Media in the Preparation of the SAO Annual Work Program for 2025.” The workshop focused on presenting the results of the SAO’s work, outlining the audit performance process, and discussing the development of the SAO’s Annual Work Program for 2025. Civil society organizations and media representatives actively contributed valuable suggestions for audits.

As of the day of preparation of the 2025 SAO Annual Work Program, 122 requests for audit were received, most of which were requests submitted by institutions and legal entities (59%) NGO citizens and anonymously 37%, local self-government units (LSGUs) 2%, media 2%.  In 2025 SAO Annual work program, out of the total received requests for audit, the State Audit Office accepted 44 requests for audit or 36% of the total received requests. For more information about SAO Annual program, can be found on the following link: GP_2025_Drzaven_zavod_revizija.pdf

In the reporting period, SAO participated in bilateral and international meetings, seminars and events for professional development and exchange of experiences in order to improve the impact of audits, which will highlighted: Contact Committee of the Heads of SAIs of the European Union and the European Court of Auditors, in Cyprus; annual meeting of the International Board of NATO Auditors (IBAN) in NATO headquarters in Brussels, EUROSAI WGEA Spring Session held in Floriana, Malta, Annual Meeting of the EUROSAI Working Group on Municipality Audit (WGMA) and the 7thSeminar "Infrastructure projects at the local level", in Tbilisi, Georgia, Annual meeting of the EUROSAI Working Group on Environmental Auditing (EWGEA), in Baku, Azerbaijan; Annual Meeting of the INTOSAI Working Group on Public Debt (WGPD); 6-th EUROSAI Young Congress on the topic of Artificial Intelligence, in Poland;  Conference on the topic of "Audit of Political Parties and Financing of Election Campaigns", organized by SAI of  Slovakia, Disinformation and the Importance of Public Trust in Data, organized by the EUROSAI Resilience & Preparedness Project Group;  Seminar on ESG issues, organized by SAI od Slovakia; Conference “Expenditure reviews as a tool on Strengthening Fiscal Governance" in Viena, the second meeting of the EUROSAI SG1 Project Group on Benefits and Methodologies of Real Time Audit, organized by the SAI of Italy in cooperation with the SAI of Hungary; 26th UN/INTOSAI symposium on "Implementation of the Sustainable Development Goals/ Goal 13 - Action to address climate change; The International Conference of Auditors 2024,  e-seminar on the topic “Government IT Expenses – are they under control”, organized by the EUROSAI IT Working Group; webinar on the 30 April 2024 organized by the EUROSAI SG1 Project Group “Traveling Club of Experts” on advance sampling method in audits and the final meeting; SAI Innovation Marketplace Webinar on the SDG audit, and presentation of the IT solution of SAI Malta.

During the reporting period, the State Audit Office engaged in significant bilateral activities, including hosting numerous international delegations led by the Chief State Auditors of the Supreme Audit Institutions of Slovenia, Malta, Czech Republic, Slovakia, Bosnia and Herzegovina, President of the International Board of Auditors for NATO, as well as undertaking high-level bilateral visits with the President of EUROSAI, President of the European Court of Auditors, Heads of the SAI of Italy, Albania, Turkey, Poland, Slovakia, Czech Republic, Montenegro and others. This visit allowed for an exchange of experiences on shared interests and discussions about opportunities to enhance cooperation between SAIs. The commitment for continuous professional and technical cooperation for strengthening professional capacities and promoting accountable and effective external audit has been translated into the contents of the signed Memorandums of Cooperation between the supreme audit institutions, between Heads of the SAI of Republic of North Macedonia heads of SAI of Italy, Montenegro, Internatilal Bord of Auditors of NATO and etc.

At the end of 2024, the State Audit Office (SAO) prepared the Report on the Functional Analysis, documented under No. 47-1174/2 dated December 30, 2024. This report is intended for the Government's consideration. The functional analysis was prepared based on the Government conclusions, having in mind SAO obligation from the  Reform Reform Agenda, as well as SAO obligations arising from the Roadmap for Public Administration Reform and the commitments related to the provisions of the new Budget Law, including obligations from inter-institutional cooperation with the World Bank. Considering these insights, the Report on the conducted functional analysis presents recommendations for amendments to the SAO Act for internal systematization with new job positions.

At the same the SAO has informed the Minister for EU integration that in the ANNEX VI of the Commission Implementing Decision approving the Reform Agendas and the multiannual work program under the Reform and Growth Facility for the Western Balkans Reform And Growth Facility For The Western Balkans (Reform Agenda of North Macedonia 2024-2027), approved by the European Commission on 23.10.2024, except in point 16 Control and Audit, no specific activities (steps) and funds are foreseen for the State Audit Office (SAO). It is essential to plan activities and funds to effectively meet the requirements established for the State Audit Office (SAO) as detailed in the Reform Agenda. This is especially important because the SAO is required to carry out activities in accordance with Regulation (EU) 2024/1449 with aims to enhance the SAO's capacities.

The activities for further strengthening of capacities for conducting audits are expected to ensue in accordance with SAO strategic and planning acts as well as with planned project activities.

Activity 3: Increasing SAO visibility and communication with stakeholders

The State Audit Office in November 2024, marked its significant jubilee – 25 years as a guardian of public funds. On this occasion, the SAO, partially supported by EUROSAI, organized a conference in Skopje under the topic “Exchange of Experiences in the SAIs Communication Process with Stakeholders – Opportunities and Challenges,” which brought together Auditor Generals from supreme audit institutions, experts from the academic community, professional associations, representatives of civil society organizations and media. Three panel discussions facilitated the exchange of experiences, ideas, and solutions focused on improving communication processes and methodologies in Supreme Audit Institutions (SAIs), along with addressing key challenges and opportunities in stakeholder communication.

The SAO is actively implementing its Communication Strategy to enhance transparency, accountability, and access to information about its operations. As part of these efforts, the SAO has expanded its stakeholder base, now reaching 1,215 individuals and organizations, ensuring broader dissemination of its final audit reports and related updates.

SAO has also continued with the practice of preparing audit abstracts and press releases for the public, where key shortcomings/information contained in the final audit report are presented in a simple and comprehensible way, as well as sending the information on the published final audit report to all stakeholders and posting it to SAO Facebook page.

SAO continuously monitors visits to its Website/Facebook, which indicates that the SAO maintains a high level of transparency. The total number of visits to the SAO website in 2024 is 221,718, representing 144% of the visits (144,640) in 2023 and 440% of the visits (48,184) in 2020.

SAO actively uses Facebook, YouTube and LinkedIn as channels for communication with the stakeholders. From the creation of the SAO Facebook page until December 31, 2024, the total number of visits recorded on the SAO Facebook page is 2,077,768, with an average of 2,678 visits per day and 9,324 followers.

For improved visualization and promotion of SAO activities and operations, video clips were prepared for final audit reports and uploaded to the SAO YouTube channel and Facebook page.

In 2024, the Auditor General and SAO representatives participated in 13 (thirteen) TV news and investigative journalist shows, thus promoting transparency and raising awareness of the public regarding the necessity to overcome detected weaknesses and act upon recommendations contained in the audit reports.

In 2024, the State Audit Office continued with the public survey as a tool for researching the opinion and impact of SAO work among stakeholders. To improve quality and strengthen transparency, accountability and visibility in its work, the State Audit Office sent a questionnaire/survey on the degree of satisfaction with SAO cooperation and information about the work of our institution to all 1.200 stakeholders: 698 institutions, 324 media and 178 civil society organizations. According to the structure of answers received in relation to the question of satisfaction with SAO cooperation, 93% of respondents expressed satisfaction with SAO cooperation, noting that a great step forward has been made in terms of openness and cooperation with SAO, particularly, timely information about issued audit reports, about SAO activities, and the openness towards the media and civil organizations has increased. Great confidence was also expressed in SAO work, assessing it as an impartial, independent, legal, objective, transparent and professional institution. There is no lack of satisfaction with the quality of final audit reports issued, which are assessed as topical, understandable, accurate and objective.

in May 2024, Certification body performed the recertification review. The Report stated that SAO management system is fully compliant with the requirements of the standard MKC EN ISO 9001: 2015, thus extending the validity of the certificate and confirming that SAO applies the Management System in accordance with the requirements of the ISO standard until 30 May 2027.

In 2024, several workshops were held in order to strengthen the cooperation between the State Audit Office and the Public Prosecutor's Office of the Republic of North Macedonia (PPO), with focus on the methodology and SAO operation in the preparation and content of the final audit reports as well public prosecutor's procedure. These workshops were organized with the support of the WFD. Frequent meetings between SAO employees and Public Prosecutors to provide information and clarification about the findings presented in the audit reports, as well as exchange information upon submitted a request and received feedback from the Public Prosecutor’s Office regarding the activities undertaken based on the final audit reports submitted over the last five years. Both institutions are implementing the adopted the internal mandatory guidelines for further actions which should contribute to more effective communication and cooperation between the SAO and PPO.

A delegation from the State Audit Office (SAO), led by Auditor General, and the Public Prosecutor's Office of North Macedonia, visited Poland's National Audit Office and National Prosecutor's Office. Organized by the Westminster Foundation for Democracy, the visit focused on exchanging knowledge and best practices regarding the roles of state auditors and public prosecutors in addressing audit reports and enhancing their communication and coordination.

Representatives from the SAO participated in several coordination meetings with members of the Public Prosecutor's Office, the State Commission for the Prevention of Corruption, the Public Procurement Bureau, and the Inspectorate Council. These meetings focused on establishing effective coordination mechanisms among key institutions to prevent and combat corruption. This topic is particularly important as it highlights the need to develop efficient working and communication tools for the rapid determination of jurisdiction. This approach aims to minimize overlaps and optimal usage of limited resources in the fight against corruption. These workshops were organized with the support of a USAID project.

On 5 December 2024, at the State Commission for Prevention of Corruption invitation, Auditor General participated in a formal event at the Assembly of the Republic of North Macedonia in observance of International Anti-Corruption Day. The event was organized as part of the USAID Anti-Corruption Partnership Project and the "Communities with Integrity" project funded by the Government of Switzerland and implemented by the National Democratic Institute.

SAO, represented by the Auditor General actively participated in the work of the Interdepartmental Body for the Coordination of anti-corruption activities. This body was established by a government decision to strengthen the cooperation between competent institutions for the purpose of promoting the policies and mechanisms for prevention and dealing with corruption.

On 18 January 2024, employees of the State audit Office and the Office of the Deputy Prime Minister in charge of good governance policies held a workshop on "Improving methods for best use of data and recommendations contained in SAO final audit reports". Apart from the representatives from these two institutions, the workshop was attended by professor of criminal law and GRECO representative in the country, and investigative journalist and TV producer.

The State Audit Office, represented by Auditor General Maksim Acevski, actively participated in the first meeting of the advisory body for the process of creating the Investment Map. This project marks a new phase of the National Development Strategy (2024-2044) implemented with the support of the United Nations Development Programme (UNDP). This initiative will provide a clearer picture of the key sectors that will lead the country toward sustainable growth and development. The participation of the State Audit Office in this process is of vital importance, as the institution will provide expert audit support to monitor the implementation of these significant projects.

Representatives of the State Audit Office in period April – June 2024 participated in the series of meetings on increasing the impact of the audit through stakeholder engagement, that were organized under the Constituency Programme 2024 and implemented by the Netherlands Court of Audit.

Under the signed cooperation agreement, a cooperative performance audit was conducted on "Gender equality and empowerment of women from rural areas through their inclusion in the labor market," coordinated by the State Audit Office (SAO) of North Macedonia with the Supreme Audit Institutions (SAIs) of Albania and Kosovo. For this audit on 17 July 2024, SAO hosted a promotional event with Albania and Kosovo, presenting the Joint Audit Report, supported by UN Women. The report highlighted regional challenges, identified shortcomings, and provided recommendations for improving gender equality and economic empowerment of rural women. This report was reviewed by the Committee on Equal Opportunities for Women and Men on 15 October 2024. Additionally, a SAO delegation, led by the Auditor General, participated in the 68th Commission on the Status of Women at the UN Headquarters in New York on 12 March 2024. SAO, with UN Women’s support, hosted a side event on the role of supreme audit institutions in increasing accountability in gender equality financing and auditing SDG 5, sharing experiences from the Western Balkans. For several years now, SAO, as the supreme audit institution of the Republic of North Macedonia, has been successfully conducting gender audits in collaboration with UN Women, making a significant contribution to advancing gender equality in policies and measures in the country, the region, and beyond.

As a result of the successful collaboration between the State Audit Office of the Republic of North Macedonia and the State Audit Institution of the Republic of Serbia, a cooperative performance audit was completed on the topic "Preparedness of the Republic of North Macedonia and the Republic of Serbia for the implementation of the Sustainable Development Goals by 2030." On 22 May 2024, the SAO hosted a promotional event for presentation of the results of the parallel performance audit on the topic of “Preparedness for implementation of the Sustainable Development Goals until 2030”, with support of the UNDP and participation of representatives from the Supreme Audit Institutions of Serbia and Slovak Republic and relevant stakeholders. Additionally on 31 May 2024, in the premises of the Faculty of Economics at the University "St. Cyril and Methodius" - Skopje, a workshop for SAO employees was held for presenting the methodology of auditing Preparedness of the country for implantation of SDG by 2030 as well as presenting the Final Audit Report on "Preparedness of the Republic of North Macedonia for the implementation of the Sustainable Development Goals until 2030" and the Joint audit report on the parallel performance audit "Preparedness for the implementation of the UN Sustainable Development Goals until 2030" conducted between the SAO and the State Audit Institution of the Republic of Serbia. These reports, along with subsequent joint activities and events, was carried out with the support of the United Nations Development Programme (UNDP).

In order to answer the question of whether the competent institutions in the Republic of North Macedonia undertake measures and activities for the continuous improvement of the student standard, the State Audit Office carried out an audit to determine the efficiency of the measures, policies and projects for fulfilling the conditions in which the state dormitories operate in Republic of North Macedonia and the development of the student standard. The audit also includes an expert opinion regarding the "Economic cost of accommodation in state dormitories", and "Students' perception of the functioning and conditions in student dormitories". Due to the importance of the audit, a presentation and discussion with stakeholders to promote the report, was held on 27 March 2024. This activity is part of the project Democracy Works, implemented by the WFD and financed by the British Embassy Skopje.

The annual report on performed audits and operations of the SAO has been submitted to all Supreme Audit Institutions, the European Court of Audit, INTOSAI and EUROSAI, the Delegation of the European Union in the Republic of North Macedonia, the missions of international organizations as well as certain diplomatic missions in the Republic of North Macedonia.

On 23-24 December 2024, with the support of the Westminster Foundation for Democracy, SAO organized a training session on public speaking and public address. The session aimed to improve communication skills for effective public appearances including press conferences, TV appearances, and giving statements and interviews. The training was intended for the management and part of the employees.

In the period of 2024, the Auditor General signed several Memoranda of Cooperation (MoCs) with key institutions in the country. In January, the MoC with the Minister of Health was signed to enhance data exchange and healthcare reporting for the State Audit Office. In February, a MoC with the President of the Fiscal Council aimed at improving cooperation in fiscal and macroeconomic policies, data sharing, and technical support. On September 30, the Auditor General and the Secretary General of the Red Cross signed a MoC to strengthen their partnership, which was marked by a blood donation campaign in celebration of the 25th anniversary of the State Audit Office. On November 1, the State Audit Office, the Ministry of Education, and "St. Cyril and Methodius" University signed a MoC to foster coordination in higher education.

Further increase of SAO visibility and communication with stakeholders is expected with the implantation of the new SAO Communication Strategy 2024-2027 with support of WFD.

# Priority 2: Parliamentary Oversight

Measure 1: Establishing a mechanism for reviewing audit reports and the measures taken following the recommendations given in the audit reports in the RNM Assembly

The State Audit Office (SAO) timely and objectively informs the Parliament about its work, about the audit findings from the conducted audits, provides support to the Parliament in fulfilling part of its competences by identifying and presenting irregularities, non-compliance with legal regulations, illegal handling of public funds and possible cases of corruption and abuse of official duty, which is why communication with the Parliament is considered particularly important.

The cooperation between the SAO and the Parliament takes place continuously in several directions and is realized through the following forms determined by the Law on State Audit and the Memorandum on Cooperation:

- submission of the Annual work programme to the Parliament for information;

- submission of the Annual Report on the performed audits and operation of the SAO to the Parliament for review, and the Parliament adopts conclusions thereon;

- submission of final audit reports to the Parliament;

- submission summary reports from final audit reports by separate areas.

Within the framework of the project activities contained in the Twinning project "Improving external audit and parliamentary supervision "MK 18 IPA FI 03 20, several activities were carried out, including the following:

- A memorandum of cooperation (MoC) between the Assembly of the Republic of North Macedonia and the State Audit Office was signed at the closing conference of the Twinning project on October 21, 2022.

- several written procedures of the SAO and the Assembly have been developed for the delivery and review of audit reports and other documents to/by the Assembly. They will be final after the adoption of the new Law on State Audit and adjustment of the content of the procedures with it.

In accordance with the signed Memorandum of Cooperation, in 2024, two summary reports were prepared and submitted to the Parliament in accordance with the Annual Work Program of the SAO for 2023, namely:

- summary report on performed audits of financial statements and compliance audits of the Local Self-Government Units and

- summary report on regularity audits of Public Health Institutions.

In the next period, the following activities should be implemented:

- implementation of concluded Memorandum of Cooperation between the Assembly and the SAO and

- preparation of final/proposal procedures in the SAO and the Assembly for submission and review of audit reports and other documents.

Measure 2: Strengthening institutional capacities for reviewing audit reports in RNM Assembly

Within the project activities included in the Twinning project "Improving External Audit and Parliamentary Oversight "MK 18 IPA FI 03 20, within the framework of Component 3, several activities were carried out, including the following:

- a new Manual "The role of the State Audit Office and the Parliament in strengthening the efficiency in the management of public finances" is prepared and printed copies of this manual will be provided to Parliament.

- proposals for amendments to the internal acts of the Assembly have been prepared and

- an Action Plan has been prepared with activities to improve the cooperation between the SAO and the Parliament for the submission and review of audit reports.

In the next period after the adoption of the new State Audit Law, the following activities should be implemented:

- preparation of a Training Plan for MPs and employees of the RNM Assembly Service in order to facilitate the understanding of the audit reports and preparation for a debate on the audit reports.

- conducting trainings in accordance with the Training Plan for the Members of Parliament and employees of the RNM Assembly Service in order to facilitate the understanding of the audit reports and preparation for the debate on the audit reports and

- Implementation of activities for strengthening cooperation with Committee on Financing and Budget, Parliamentary Institute and the Parliamentary budget office of the RNM Assembly.

The preparation of a training plan for parliamentarians and employees of the RNM Assembly Service in order to facilitate the understanding of the audit reports and preparation for a debate on the audit reports, as well as the preparation and realization of at least three training sessions for the parliamentarians and employees of the RNM Assembly Staff of the Parliament, planned within of the Twinning project were cancelled by a letter from the Parliament. The main reason for the non-implementation of the activities was the unsigned Memorandum of Cooperation during the period when the activities were supposed to be implemented.

With support of the National Democratic Institute, several workshops were organized in 2024 in which representatives from SAO and the Parliament took part. More significantly is the study trip/workshop organized and financed by NDI between the Swiss Parliamentary Service and the Service of the Assembly of the Republic of North Macedonia, in the Parliament in Bern, in the period from February 19 - 20, 2024, in which representatives from SAO and the Assembly participated (The Parliamentary Budget Office and the Committee on Financing and Budget).

In 2024 several final audit reports were discussed or public hearing was organised by committees and bodies within the Assembly.

On 22 October 2024, for the first time since the SAO establishment, final audit report on performance audit was considered and discussed at the plenary session of the Assembly.

The consideration and discussion of an individual final audit report by a committee and at a plenary session in the Assembly results from the signed Memorandum of Cooperation between the State Audit Office and the Assembly of the Republic of North Macedonia, in which consideration of individual final audit reports of the SAO is envisaged.

# Pillar VIII - PFM at Local Level

# Priority 1. Fiscal Decentralisation

Measure 1: Improving Fiscal Capacity and Increasing Municipal Revenues

The new Law on Financing Local Self-Government Units will further regulate financial operations and strengthen the financial independence of municipalities, as well as align it with the provisions of the new Law on Budgets.

With the technical assistance of UNDP, an assessment of the municipal financing system and the existing Law on Financing of Local Self-Government Units was carried out in 2022. This assessment aimed to identify weaknesses and potential opportunities for improving the financial system at the local level. The conclusions and recommendations obtained from this assessment will be key for the preparation of the new Law on Financing of Municipalities.

The activities related to the preparation and adoption of the new Law have been postponed, taking into account that additional amendments have been made to the new Law on Budgets, whereby the entry into force of the provisions of this Law, which also relate to the financial operations of municipalities, has been postponed. The activities will begin to be implemented in the second half of 2025. This delayed start of the implementation of the activities depends on the entry into force of the amendments to the new Law on Budgets, as well as on the functionality of the IFMIS system, which is key to the effective implementation and monitoring of public finances, so its functioning is a condition for the successful implementation of the activities.

The amendments made to the Law on Financing Local Self-Government Units in 2022 have ensured an increase in the percentage of revenues that municipalities receive from various sources. Thus, the percentage of VAT revenues distributed to municipalities gradually increased from 4.5% to 6%. In 2024, municipalities received 6% of the collected VAT from the previous year, i.e. 4,202 million denars, which is an increase of 640 million denars compared to 2023. From personal income tax revenues in 2024, municipalities secured income of 6% of the collected personal income tax from salaries of individuals, according to their place of residence. In total, this amounted to 1,271 million denars, which is an increase of 352 million denars compared to 2023.

These changes have provided a significant improvement in the fiscal capacity of municipalities and more funds for financing local projects and services.

During 2023-2024, USAID has established a Project for the Improvement of Local Self-Government and Revision of the Legal Regulation Regarding Local Taxes. Amendments to the Law on Property Taxes were prepared and presented to the Ministry of Finance.

During this period, with technical assistance from UNICEF, the World Bank and SIGMA, analyses of the existing criteria for the allocation of block grants in primary education and culture were conducted and recommendations were made for determining new criteria for the allocation of block grants. In addition, within the framework of technical assistance from UNDP, a comparative analysis was carried out with neighboring countries and EU Member States regarding the allocation of capital transfers, during which an Excel tool for the allocation of capital grants was prepared.

Considering that these activities are not under the direct jurisdiction of the Ministry of Finance, they are not foreseen in the Public Finance Management Program for the upcoming period. However, the Ministry of Finance will be actively involved if there are initiatives from the competent ministries that require support or coordination.

Measure 2: Regional and Local Development

The working group formed to draft legal solutions for the establishment of the Agency for Regional and Local Development, which was composed of representatives of various ministries and institutions, in 2023 analyzed the experiences of other countries that have similar institutions and proposed possible models for the transformation of the Bureau for Regional Development into an Agency. The Ministry of Local Self-Government assumed responsibility for processing the guidelines of the Working Group and preparing the information that was submitted to the Government. The Government, after reviewing the proposed scenarios, decided to take measures to draft legal solutions that would enable the establishment of the new Agency for Regional and Local Development. Considering that these activities are not in accordance with the Government Program 2024-2028, this activity will not be implemented in the coming period.

# Priority 2: Financial Discipline, Transparency and Accountability at Local Level

Measure 1: Increasing the Financial Discipline

The amendments to the Law on Financing Local Self-Government Units from August 2022 provide for more realistic planning of municipal budgets, whereby own revenues in the municipal budget can be planned with an increase of 10% of the average realized revenues in the last three years. In doing so, it is possible if the municipality realizes its own revenues above 75% of the planned ones by the third quarter, to additionally increase its revenues up to a maximum of 20%, starting in 2025. For 2024, revenues were planned with an increase of 15% above the average with an additional 15% by the third quarter. As a result of this rule, at the end of the year it was concluded that the percentage of realization is over 90%, which indicates better planning of revenues.

In 2025, revenues are planned with an increase of 10% with an additional 20% if the realization of own revenues by the third quarter exceeds 75% of the planned ones. During this period, LSGU budgets are regularly monitored and controlled to ensure that they are prepared in accordance with existing legal regulations, while budget execution is also monitored.

In the ESPEO system, overdue liabilities are monitored, which represent debts that municipalities need to pay. Municipalities enter the data on a monthly basis, and quarterly data is published on the website of the Ministry of Finance.

Quarterly monitoring of overdue liabilities and fulfillment of the conditions for declaring financial instability is particularly important for timely identification of municipalities that may face problems in managing their finances. This may be a prerequisite for introducing measures to protect financial stability.

When it is determined that a municipality meets the conditions for declaring financial instability, but it has not been declared as such, the Financial Inspection is notified.

In the coming period, continued monitoring of the overdue outstanding liabilities of municipalities is of crucial importance. By regularly monitoring these liabilities, situations in which municipalities will not be able to meet their financial obligations can be prevented. Continuous monitoring of the fulfillment of the conditions for declaring financial instability is of crucial importance for timely determination of whether a municipality should be declared financially unstable.

Measure 2: Increasing the Transparency and Accountability throughout the Operations of the Municipalities

After entering into force of the new Law on Financial Inspection in the Public Sector (*) (“Official Gazette of Republic of North Macedonia” no.19/23), on 7th of February 2023, within the reporting period ending with 31th of December 2024, a total of 261 submitted applications for financial inspection of public sector entities at the local level were acted upon.

The publication of data on municipal finances and their transparency plays an important role in the management of public funds and ensuring financial accountability. Thus, during this period, data on realized revenues and expenditures of municipalities for the fourth quarter of 2023 and the three quarters of 2024, data on overdue unpaid liabilities from the ESPEO system, the Final Account of the Budget of the Republic of North Macedonia for 2023, including the final accounts of municipalities, have been published on the website of the Ministry of Finance. With the support of UNDP, financial indicators are published on the websites of municipalities and the Ministry of Finance. The publication of financial indicators from the periodic financial reports for about 55 municipalities on their websites, as well as on the website of the Ministry of Finance, provides public insight into the finances of municipalities and facilitates monitoring of their financial situation.

Future steps to be taken in the coming period are aimed at improving transparency, accountability and timely publication of financial data. These activities will improve the management of public resources and help monitor the financial situation of municipalities.

Monitoring and Coordination

The monitoring process is based on the PFM reform management and coordination framework, comprising the following structures established at all hierarchical levels of decision-making.

•	PFM Council

•	PFM Working Group

•	Priority Coordinators

•	Coordination Unit within

MoF

PRFM Reform Programme 2022-2025 sets indicators and targets by year for each planned activity. As regards PFM sub-sector, Performance Assessment Framework integrates the indicators and the targets for the PRFM Reform Programme, and the responsibilities for data collection and processing are being assigned on the grounds of the monitoring and reporting system envisaged in the Programme.

Strong political commitment as regards the fulfilment of the reform goals set in PFM Reform Programme 2022 - 2025 is ensured through the PFM Council.

The Government established the PFM Council on 12th February 2018 (“Official Gazette of the Republic of Macedonia”, no. 28/2018), as the highest-level coordination body, the primary goal of which is to ensure full political commitment in achieving the reform goals under the PFM Reform Programme 2018-2021.

On 14th June 2022, the Government adopted a new Decision on Establishment of PFM Council, as the key body within the structure for managing, coordinating, monitoring and reporting about the implementation of PFRM reform Programme 2022 - 2025.

In March 2024, the PFM Council has conducted a consultation following a written procedure on the draft Monitoring Report on Implementation of the 2024 Action Plan for PFM Reform Programme for the period January–June 2024 after which during August 2024, the Draft Report was adopted by the Government.

PFM Sector Working group is a technical working body established by the Minister of Finance for the purpose of preparing, monitoring and reporting on the PFM Reform Programme. It comprises members and observers nominated by the relevant institutions included in activities related to PFM sector (ministries and other public entities, civil society organisations, development partners). The Working Group was initially established under a Decision adopted by the Minister of Finance on 10th June 2015, and it has been modified and amended several times since, with the recent amendment made on 3th July 2023.

IPA and NPAA Unit within MoF represents the Coordination Unit, acting as a technical secretariat to support the functioning of the PFM Working Group and the PFM Council. In general, its tasks comprise technical preparation of the meetings of the PFM Council and the PFM Working Group and preparation of compiled reports on the progress as regards the implementation of the reforms under each priority and compiled annual action plans, based on the input provided by the Priority Coordinators.

These working bodies also ensure the necessary coordination among all PFM sub-system strategies and policies (PIFC Policy Paper, Tax System Reform Strategy, PRO and CARM strategies), as well as the other related national strategies, such as the Public Administration Reform Strategy.

Meetings of the PFM SWG are held regularly both at the policy and technical level.

On the technical level, SWG meetings are held on concrete PFM sub-areas measures, including on IPA II and IPA III programming and implementation.

On February 24, 2023, a technical meeting of the SWG was held to discuss the possibility of using the EU Integration Facility mechanism within the IPA framework to finance new projects in the field of public finance management. Project Proposals in the area of ​​public revenues and tax and customs policy, in the area of ​​the Academy of Public Finance, inspection in the public sector, as well as public internal financial control were submitted to NIPAK on April 4, 2023 with the aim of forwarding them to the EU Delegation. Until now, no answer has been received as to whether they have been approved by the EC.

On April 28, 2023, a technical meeting was held with the PFM SWG to discuss the Draft Monitoring Report on Implementation of the 2022 Action Plan for PFM Reform Programme for the period January–December 2023, and the Draft 2023 Action Plan.

On September 21, 2023, a technical meeting was held with the PFM SWG to discuss the Draft Monitoring Report on Implementation of the 2023 Action Plan for PFM Reform Programme for the period January–June 2023.

On 28 March 21 April 2024, a technical meeting was held with the PFM SWG to discuss the Draft Monitoring Report on Implementation of the 2022-2023 Action Plan for the PFMS Reform Program for the period January - December 2023 and the PFM Reform Program 2024-2027 with the Draft Action Plan for 2024.

# Financing of the PFM Programme for 2024

The following table presents the planning and realisation of the budget for the implementation of the reform activities of the PFM Reform Program for 2024.

| Pillars | Priority | Budget(Eur) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | National budget |  | Donor funds |  | Total |  |
|  |  | Planned-2024 | Realised | Planned-2024 | Realised | Planned 2024 | Realised |
| I Economic Analysis, Macroeconomic and Fiscal Framework | 1.Revenue forecasting and reporting | 0 | 0 | 200,000 | 50,000 | 200,000 | 50,000 |
|  | 2.Economic analysis and Macroeconomic forecasting | 118,669 | 79,231 | 116,000 | 116,000 | 234,669 | 195,231 |
|  | 3.Strengthening Debt Management | 12,240 | 0 | 0 | 0 | 12,240 | 0 |
| II Revenue Mobilization | 1.Tax and customs policy | 0 | 0 | 170,000 | 0 | 170,000 | 0 |
|  | 2.Tax administration | 2,577,000 | 0 | 0 | 0 | 2,577,000 | 0 |
|  | 3.Customs | 440,000 | 440,000 | 350,000 | 350,000 | 790,000 | 790,000 |
| III Planning and Budget | 1.Budget Planning | 12,000 | 12,000 | 112,300 | 112,300 | 124,300 | 124,300 |
|  | 2.Strengthened Public Investment Management | 0 | 77,971 | 0 | 64,000 | 789,100 | 141,971 |
|  | 3.Effective instruments under the Growth Acceleration Plan | 0 | 0 | 0 | 0 | 0 | 0 |
| IV Public procurement | 1.Public Procurement Policy | 80,000 | 15,500 | 0 | 0 | 80,000 | 15,500 |
|  | 2.Public Private Partnerships (PPPs) | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 3.Appeal mechanism | 0 | 0 | 0 | 0 | 0 | 0 |
| V Integrated Public Finances | 1.IFMIS | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 2.Strengthen the Accounting of Budgets and Budget Users | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 3.Public Finance Academy | 56,000 | 0 | 0 | 0 | 56,000 | 0 |
| VI Public Internal Financial Control | 1.Financial Management and Control | 0 | 0 | 10,000 | 10,000 | 10,000 | 10,000 |
|  | 2.Internal Audit | 10,000 | 10,000 | 10,000 | 10,000 | 20,000 | 20,000 |
|  | 3.Financial inspection | 0 | 0 | 0 | 0 | 0 | 0 |
| VII External Control and Parliamentary Oversight | 1.External audit | 0 | 0 | 327,000 | 200,000 | 327,000 | 200,000 |
|  | 2.Parliamentary Oversight | 0 | 0 | 130,000 | 20,000 | 130,000 | 20,000 |
| VIII PFM at Local Level | 1.Fiscal decentralisation | 7,000 | 0 | 0 | 0 | 7,000 | 0 |
|  | 2.Financial Discipline, Tranparency and accountability on local level | 35,600 | 0 | 0 | 0 | 35,600 | 0 |
| Total |  | 3,348,509 | 634,702 | 1,425,300 | 932,300 | 5,562,909 | 1,567,002 |
| Out of which for GAP instruments: |  | 0 | 0 | 0 | 0 | 0 | 0 |
| TOTAL without GAP instruments |  | 3,348,509 | 634,702 | 1,425,300 | 932.300 | 5,562,909 | 1,567,002 |

# Annexes

# Annex 1: Monitoring matrix of the PFM Reform Programme for the year 2024

# Annex 2: Risk assessment of the PFM Reform Programme for the year 2024

Annex 3: Selected results achieved in the period 2022-2024

https://finance.gov.mk/wp-content/uploads/2024/01/ERP-2024-2026-EN.pdf

https://economy-finance.ec.europa.eu/publications/2024-economic-reform-programmes_en

At the session on January 14, 2025, the Government adopted the draft Economic Reform Program 2025-2027, which was officially submitted to the European Commission on January 15, 2024 and published on the MoF website:

https://finance.gov.mk/wp-content/uploads/2025/01/ERP-2025-2027_MKD-1.pdf

https://dzr.mk/sites/default/files/2023-01/Strategija_za_%20razvoj_na_%20DZR_2023_2027.pdf

https://dzr.mk/sites/default/files/2023-06/IT_Strategija_DZR_2023_2027.pdf

https://www.fsovet.mk/%d0%b8%d0%b7%d0%b2%d0%b5%d1%88%d1%82%d0%b0%d0%b8-%d0%b8-%d0%bc%d0%b8%d1%81%d0%bb%d0%b5%d1%9a%d0%b0/

It is important to note that the activity in question was carried out largely within the framework of the above mentioned Twinning project, and in the period from April 2020 to June 2022, the following activities were carried out:

- GAP analysis of the Customs Law, Law on Excise Duties, VAT Law, Tax Procedure Law, Profit Tax Law, A and B Accounts (traditional own resources), Personal Income Tax Law, Motor Vehicle Tax Law, Law on Public Revenue Office, as well as the track and trace legislation, and

- Reviewing the results from the carried out GAP analysis of the Personal Income Tax Law, Law on Customs Administration, Law on Property Taxes, Law on Excise Duties, Customs Law, VAT Law, Law on Customs Measures for Protection of Intellectual Property Rights, Law on Customs Tariff, Tax Procedure Law, Profit Tax Law and preparation of recommendations for the improvement of these laws.

https://dzr.mk/sites/default/files/dzr/doc/MoU_Peer_Review_SAI%20Poland_Macedonian_signed_MKD.pdf

ЕНЕР | Предлог на Закон за вработените во јавниот сектор

ЕНЕР | Предлог Закон за стручно усовршување и обука на административните службеници

ЕНЕР | Предлог на Закон за административни службеници

Rulebook for Organizational classification (Official Gazette of the Republic of North Macedonia” no 277 from 31.12.2024)

GUID 9030 - Good Practices Related to SAI Independence; INTOSAI – P-12 - The Value and Benefits of Supreme Audit Institution making a difference to the lives of citizens; Un Resolution 69/228 and 79/231 Promoting and fostering the efficiency, accountability, effectiveness and transparency of public administration by strengthening supreme audit institutions; INTOSAI-P 10 - Mexico Declaration on SAI Independence; INTOSAI-P 1 - Lima declaration;

: https://dzr.mk/sites/default/files/2023-01/Strategija_za_%20razvoj_na_%20DZR_2023_2027.pdf

https://dzr.mk/sites/default/files/2023-12/Godisen_plan_KPU_DZR_2024.pdf

Organized by World Bank’s Enhancing Accounting, Auditing and Sustainability Reporting (EAASURE) program, funded jointly by the Austrian Ministry of Finance and SECO, implemented by Center for Financial Reporting Reform.

https://dzr.mk/.../Zaklucoci_GI_DZR_2023_Sobranie_RSM...

Conclusion number 2 from the Draft Minutes of the 31st thematic session of the Government of the Republic of North Macedonia, held on November 12, 2024 (number 41-11471/2), the SAO was instructed to analyze employment needs based on a functional analysis of necessary profiles and competencies. Additionally, in connection with conclusion number 5 from the Draft Minutes of the 33rd session of the Government, held on November 19, 2024 (number 41-11841/4), the SAO was obligated with operationalizing the Rapid and Growth Facility (Reform Agenda). This involves preparing all necessary procedures, instructions, guidelines, and documents for monitoring, reporting, evaluation, public internal financial control, and audit, related to the implementation of the Reforms and Growth Facility. This should be completed no later than the ratification of the Agreement for the Instrument by the Parliament of the Republic of North Macedonia. Moreover, conclusions 1 and 2 from the Draft Minutes of the 36th Government session, held on December 3, 2024 (number 41-11471/6), requested the SAO to implement the required activities within the established maximum expenditure limits for the relevant fiscal year. The SAO should analyze the needs for employment, prioritizing internal reallocations before considering new employments, based on the functional analysis and workload, for the implementation of the Reform and Growth Facility by the end of December 2024 at the latest. The SAO is also responsible for informing the Government about this progress.

https://www.facebook.com/DrzavenZavodzaRevizija

Државен завод за ревизиja - YouTube

Link to the joint report: https://dzr.mk/sites/default/files/2024-05/nastan/3_Joint_report_Preparedness_of_the_countries_implementation_SDG_until_2030_EN.pdf